## CGMS-47 Plen
Plenary actions open from previous plenary sessions (at CGMS-47)
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
CGMSSEC | E.6 | A46.21 | CGMS Secretariat to organise a special plenary session or a side event on operational oceanography at CGMS-47 to help advance the operational nature of ocean observation. (Ref. CGMS-46-NOAA-WP-11, CGMS-46-IOC-UNESCO-WP-02) | 2020 Jan 22 CGMSSEC #2: CLOSURE proposed in view of CGMS A47.04 2019 Nov: An initial dedicated session on scatterometer will be held at CGMS-48. Oceanography will be addressed at future plenaries. CGMS-47: Deferred to CGMS-48 in view of the WMO constituent body reform. The CGMS Secretariat will include this session at CGMS-48 taking into account the proposal in CGMS-47 IOC-UNESCO-WP-01: Receive annual briefing on the UN Decade of Ocean Science for Sustainable Development; Sustain satellite and in situ system of ocean observing systems; Utilize geostationary meteorological satellites for ocean observations; Enhance data acquisition for special observing periods; Add CGMS-relevant ocean measurements to tsunami watch infrastructure; Add HAB toxic aerosols to coastal air pollution forecasts. (In addition to WMO-IOC coordination following the WMO constituent body reform). | CGMS-48 (CGMS-47) | CLOSED
WMO | H | A46.11 | On ocean variables: In view of the anticipated reform of JCOMM, WMO to provide a report with proposals on future coordination/cooperation between JCOMM and CGMS. | 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 as far as is possible 2019 Nov: CGMS-48-WMO-WP-xx see also A47.04 CGMS-47: In view of the WMO constituent body reform, the action is deferred to CGMS-48. 2019 Mar 13: CGMSSEC IS#3: CGMSSEC has discussed this item with JCOMM. Likely to be premature for CGMS-47, currently expected to be explicitly addressed at CGMS-48.There will however, be a presentation on sea ice monitoring in the plenary session "Observations and monitoring of the Arctic". 2019 Jan 28, WMO: CGMS should work with the JCOMM co-presidents to develop closer coordination and cooperation on mutually beneficial subjects. This is an opportunity for CGMS to learn about the wide range of activities in JCOMM. Anticipated on the agenda | CGMS-48 (CGMS-47) | OPEN
CGMS-47plenary actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
WMO | 3.1.2 | A47.01 | On WIGOS Vision 2040: WMO to report to CGMS-48 on activities undertaken to respond to the new WIGOS Vision 2040 | 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 CGMS-48-WMO-WP-xx | CGMS-48 | OPEN
WMO | 3.2.5 | A47.02 | On global NWP: WMO to provide a report at next CGMS on baseline requirements for satellite products for global NWP, to trigger a CGMS discussion on status of delivery of such observations and possible improvements in the future and inclusion in the CGMS baseline document. | 2020 Feb 19: CGMS/space agency to map the contributions towards meeting the WMO requirements. WGII and WGIII look at the process wrt critical satellite data (supply of global NWP for WMO). Adressed at the 2nd CGMS risk assessment WS 19-21 Feb 2020 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 CGMS-48-WMO-WP-xx and report from the WMO NWP workshop in May 2020. | CGMS-48 | OPEN
NOAA, WMO | 3.2 | A47.03 | On PP sector engagement: WMO and NOAA to report on the status of affairs and related issues on public private sector engagement to CGMS-48 | 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 CGMS-48-WMO-WP-xx CGMS-48-NOAA-WP-xx | CGMS-48 | OPEN
WMO, IOC-UNESCO | 3.3 | A47.04 | On operational oceanography: WMO and IOC-UNESCO to report on their coordination following the WMO constituent body reform to CGMS-48 | 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 as far as is possible CGMS-48-WMO/JCOMM-WP-xx. See also A46.11 | CGMS-48 | OPEN
IOC-UNESCO | 3.3 | A47.05 | On operational oceanography: IOC-UNESCO to provide to GCMS-48 guidance on satellite data requirement for improved coastal ocean prediction and services | CGMS-48-IOC-WP-01 | CGMS-48 | OPEN
CGMS members | 5.1 | A47.06 | WGI co-chair: CGMS members to propose candidates for the WGI co-chair |  | Q3 2019 | OPEN
CGMS members | 5.2 | A47.07 | Cloud services: CGMS agencies to analyse if existing cloud service activities can serve as a demonstration project, exploring at least two of the WMO Information Systems (WIS 2.0) principles. (Initially discussed in WGIV/8) CGMS-47-WMO-WP-20 | 2020 Jan 22 CGMSSEC #2: Members to provide further points of contact ISRO: Nitant Dube, ISRO SAC nitant@sac.isro.gov.in EUM: Lothar Wolf, lothar.wolf@eumetsat.int CMA: JMA: NOAA: (To be addressed within the framework of WGIV) 2019 Nov 22: Reminder sent to WGIV and specifically to CMA, JMA, NOAA and EUM. Members are requested to contact Enrico Fucile, Chief Data Representation, Metadata and Monitoring Division, WMO, efucile@wmo.int, cc cgmssec@eumetsat.int | Dec 2019 | OPEN | 3.7
CGMSSEC | 7 | A47.08 | Arctic observations: CGMSSEC to secure the inclusion of Arctic observations on the plenary and working group agendas for future CGMS plenary sessions | 2020 Jan 22 CGMSSEC #2: Relevant CGMS space agency members are requested to include a report on the status and plans in their agency report on plenary day 1 (in addition to the WG meetings). | CGMS-48 | OPEN
CGMS members | 7 | A47.09 | Arctic observations: Provide product priorities for Arctic observations for a special Arctic session in WG II during CGMS-48 | 2020 Jan 22 CGMSSEC #2: Added to WGII agenda. To be addressed in the report from WGII to plenary. | CGMS-48 | OPEN
CGMSSEC, CMA | 7 (5.5) | A47.10 | Hyperspectral sounding: CGMSSEC together with CMA to organise a thematic session at CGMS-48 on hyperspectral sounding observations | A thematic session will be held on day 2 of plenary (see online agenda). | CGMS-48 | CLOSED
CGMS members | 8.2 | A47.11 | Climate session: CGMS members to endorse (through a written procedure) the ECV inventory gap analysis report and updated coordinated action plan | 2020 Jan 22 CGMSSEC #2: Delayed. 2019 Nov 18: Gap analysis report and updated action plan are still being drafted due to delays in the verification of ECV entries due to slow response from agencies and subsequently delayed start of gap analysis. Report and plan should be available for review by end of November. Virtual endorsement is planned for Dec/Jan timeframe depending on review results. | Nov 2019 (Oct 2019) | OPEN
CGMS members | 8.2 | A47.12 | Climate session: CGMS members to endorse (through a written procedure) the CEOS/CGMS statement for SBSTA-51 | 2019 Nov 18: Statement endorsement validated on 15 November and statement was submitted to UNFCCC Secretariat on 17 November. CGMSSEC e-mail to main pocs of CGMS Members on 28 Oct 2019 requesting endorsement by 7 November. | Nov 2019 | CLOSED
WMO | 8.2 | A47.13 | Climate session: WMO to present implications of the WMO constituent body reform to the interface between CGMS and the requirements/GCOS at CGMS-48. | 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 as far as is possible. CGMS-48-WMO-WP-xx (to be addressed in the user session) | CGMS-48 | OPEN
CGMS members | 8.2 | A47.14 | Climate session: CGMS members are invited to provide application case studies that use climate data record to support training | 2020 Jan 22 CGMSSEC #2: Members are invited to provide case studies as necessary/available 2019 Nov 18: EUMETSAT has provided a few preliminary cases to WGClimate. CGMS members are invited to contribute. | CGMS-48 | OPEN
SCOPE-CM | 8.2 | A47.15 | Climate session: SCOPE-CM to provide an implementation plan based on the agreed new concept (ref. CGMS-47-SCOPE-CM-WP-01) | 2020 Mar 6: Unclear on way forward of SCOPE-CM, Chair stepping down? 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 CGMS-48-WP-SCOPE-CM-01 This is also a WGII action (WGII 47.09) | CGMS-48 | OPEN
WGClimate | 8.3 | A47.16 | Climate/GHG session: WGClimate to present the roadmap for the implementation of the recommendations from the GHG monitoring constellation white paper (including resource implications) | 2020 Jan 22 CGMSSEC #2: Anticipated for CGMS-48 CGMS-48-WP-WGClimate-xx 2019 Nov 18: Roadmap still under elaboration. Complete roadmap will be presented to CEOS SIT-35 late March 2020 after a wider consultation of the community that needs to exercise the implementation. | CGMS-48 (31 Oct 2019) | OPEN
CGMS members | 9.1 | A47.17 | On training and education: CGMS members active in VLab to propose the next Co‐Chair to represent CGMS satellite operators in the VLab (starting October 2020). Nominations to be presented to VLab by December 2019. | 2020 Jan 22 CGMSSEC #2: Critical! CGMSSEC to work with current co-chair to circulate a message also inviting CGMS agency representatives to the Vlab management meeting at EUMETSAT | Dec 2019 | OPEN
CGMS members | 11.1 | A47.18 | On the HLPP: CGMS members to comment on the revised HLPP text and provide feedback to CGMSSEC@eumetsat.int | New action following CGMSSEC review 27 May 2019 | 1 July 2019 | CLOSED
CGMS-47 Plenary recommendations
Lead | AGN item | Rec # | Description | STATUS (feedback for completion) | HLPP ref
CGMS space agencies | 5.7 | R47.01 | (From IPWG): IPWG strongly recommends to CGMS members to continue the constellation of PMW sensors to ensure quality satellite precipitation products for weather, climate, and hydrological applications. Additionally, IPWG would like to be kept informed of longer term plans for subsequent launches of microwave sensors to ensure continuity of long-term observations that meet the documented needs of the user community. | CLOSED in plenary and transferred to WGIII
CGMS space agencies | 5.7 | R47.02 | (From IPWG): IPWG also recommends that there be a CGMS-wide coordination of the crossing times of precipitation relevant satellites in an effort to improve the temporal sampling of diurnal cycle, convective systems lifecycles, and severe storms. | CLOSED in plenary and transferred to WGIII
CGMS space agencies | 5.7 | R47.03 | (From IPWG): As precipitation moves to higher temporal rates, we recommend to CGMS members to synchronize full-disk geostationary sampling schedules which will optimize GEO scans to improve temporal sampling of precipitation products and unknown future PMW imager availability for merged products. | CLOSED in plenary and transferred to WGIII
CGMS space agencies | 5.7 | R47.04 | (From IPWG): Collaboration between space programs and data assimilation centers should be specifically encouraged to incorporate DA requirements as part of scientific requirements when developing new satellite / observing systems. This would reduce barriers for operational assimilation of observations, and potentially provide a greater range of utility for various sensors. | CLOSED in plenary and transferred to WGIII
CGMS space agencies | 5.7 | R47.05 | (From IPWG): Higher spatial and temporal (sub-hourly) resolution and higher spectral sampling in the microwave measurement of clouds and precipitation should be considered in future observing systems. | CLOSED in plenary and transferred to WGIII
CGMS space agencies | 5.7 | R47.06 | (From IPWG): Latency and quality of satellite data should be improved, from both operational and research missions, to fit in the DA high temporal resolution cycle. | CLOSED in plenary and transferred to WGIII
CGMS space agencies | 5.8 | R47.07 | (From ICWG): CGMS members to budget a baseline funding for the intercomparison study, given its importance and impacts on global cloud products. | Also marked as a WGII recommendation
CGMS space agencies | 5.8 | R47.08 | (From ICWG) CGMS members to consider introducing multi-sensor (satellite and ground-based measurements) applications for convective nowcasting when developing/updating product requirements. | Also marked as a WGII recommendation
CGMS space agencies | 5.8 | R47.09 | (From ICWG) CGMS agencies to continue operating conically-scanning passive MW sensors in an early afternoon orbit as well as in a dusk/dawn orbit in order to maintain this unique long-term time series. | Also marked as a WGII recommendation
CGMS members | 9.1 | R47.10 | On training and education: CGMS members to provide contributions into the WMO VLab Trust Fund to ensure the continuation of technical support to the VLab. CGMS members considering to provide additional support should contact the WMO Space Programme Secretariat | 2020 Jan 22, CGMSSEC IS#2: To be addressed within the framework of Vlab, WMO, CGMSSEC plus communication to CGMS agencies

## CGMS-47 WGI
WGI actions open from previous plenary sessions (at CGMS-47)
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
DCS (WGI) sub-group | WGI/5.3 | A46.06 | The DCS sub group is invited to review and provide comments to this draft of the CGMS agency best practices in support to user DCS data access. | 2020, 28 Jan/24 March, IS: Updated Best Practice to be presentated to CGMS-48 CGMS-47 CGMS-WP-17. Proposed Best Practices to be further reviewed to take into account DCP data formats. | CGMS-48 (CGMS-47) | OPEN
CGMS members | WGI/7.2 | A46.12 | Members to provide the status of their systems already in place and those planned, along with their overall approach to dealing with the challenges associated with handling and circulating large data volumes | 2020, 24 Mar, IS: DCS Handbook published on 1 March 2020 (ref. CGMS/DOC/19/1054958 V1F) http://esww17.iopconfs.org/home 2020, 28 Jan, IS: Members are requested to provide information to CGMS-48 CGMS-47: EUMETSAT expects to report on progress to CGMS-48 in 2020. | CGMS-48 (CGMS-47) | CLOSED
CGMS-47 WGI actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
CGMS space agencies | WGI/1.1 | WGI/A47.01 | CGMS members are requested to provide nominations to the CGMS Secretariat for the position of Co-Chair of CGMS Working Group I | 2020, 28 Jan, IS: CGMSSEC to send out further reminders unless solution has been found in the course of February. | Q3 2019 | OPEN
WGI | WGI/4.1 | WGI/A47.02 | Consider the advantages of using RHCP/LHCP against the simplicity/affordability of the Direct Broadcast stations and to formulate a CGMS Agency Best Practice on use of Circular Polarisation for Direct Broadcast | 2020, 26 Feb. WGI IS: Action not explicitly discussed, but RHCP/LHCP discussed in the context of WGI/A47.03. 2020, 28 Jan, WGI IS: To be addressed in the Update of Best Practices document, section 3: Potential additional topics for consideration as CGMS Best Practice, noting that studies to be carried out in support of this work - therefore Agencies to explore the options for providing support with studies. | CGMS-48 | OPEN
WGI | WGI/4.1 | WGI/A47.03 | Analyse possible solutions to address the expected increase in instrument data from future polar orbiting satellites and to propose new DB standards and/or Best Practices as required | 2020, 26 Feb. WGI IS: Updated list of possible ways to increase the bandwidth distributed prior to meeting and discussed during meeting. Agreed to turn the list into a WP for discussion in WGI during CGMS-48. 2020, 28 Jan, WGI IS: Based on the list of possible ways to increase the bandwidth provided at CGMS-47 in CGMS-47-EUMETSAT-WP-06 , an updated/expanded list to be prepared prior to the next intersessional meeting on February 26. | CGMS-48 | OPEN
WGI | WGI/4.1 | WGI/A47.04 | Initiate a peer review process between the agencies (e.g. NOAA, CMA and EUMETSAT) of the Implementation of CGMS Best Practices for LEO Direct Broadcast Data documents prepared by these agencies, with the aim of improving quality and consistency of these documents and references prior to presentation at the CGMS plenary sessions | 2020, 26 Feb. WGI IS: Point of contact with CMA (Lei Yang) now established. NOAA, CMA and EUMETSAT will conduct the peer review during March 2020. 2020, 28 Jan, WGI IS: process initiated. Point of Contact still required from CMA. Topic also on the agenda at a bilateral meeting between CMA and EUMETSAT in February. | End 2019 | OPEN
WGI | WGI/4.1 | WGI/A47.05 | To review and if appropriate identify any common viewing geometries that are missing from the proposed list of NetCDF encoding good practices | 2020, 4 Feb, WGI IS: proposed for closure after confirming that no viewing geometries are missing from the proposed list of netCDF encoding good practices | End 2019 | PROPOSED CLOSURE
DCS sub group | WGI/5.1 | WGI/A47.06 | To coordinate the elaboration of the user requirements, the technical specifications, and potential applications for a new DCP Standard and make a proposal to WGI | 2020, 28 Jan, WGI IS: New standard document created describing possible application areas, user requirements and technical specification, initially based on ESA study. This document will be the basis for finalising the new standard. To be further elaborated at the DCS Sub-Group Meeting at the occasion of the NOAA TWG in April. Presentation of progress at CGMS-48. | CGMS-48 | OPEN
CGMS Member | WGI/5.1 | WGI/A47.07 | Review and provide comments to Draft V1B of the DCS Handbook | 2020, 28 Jan, WGI IS: Publication foreseen for Feb 2020 | Aug 2019 | OPEN
EUM | WGI/6.1 | WGI/A47.08 | Form a Space Weather Database Task Group. A first report Form the TG on its activities would be presented at CGMS-48 including: • Establish the membership and ToR of the Task Group • Establish the requirements of the Space Weather Database parameters • Establish the requirements for the Security / Confidentiality aspects • Establish the process and rules for access the Database content | 2020, 29 Jan: ISWG rapporteur (A Monham) invited CGMS agencies to nominate participants (spacecraft operations experts; spacecraft design experts in space weather resilience / standards committees; space weather service providers) and circulated draft ToRs (on the SWCG list server) 2020, 28 Jan, WGI IS: - 2020 Jan 21 SWCG IS #3: A Monham email proposal sent to SWCG 20 January for review. 2018 Oct 8, SWCG IS#2 webex: WMO noted they are compiling a catalogue of hazardous events, including space weather events, with unique identifiers. EUM/Monham to propose the ToR of the task Group as next step. | CGMS-48 | OPEN
NOAA | WGI/6.2 | WGI/A47.09 | Form a Task Group on Space Debris and Collision Avoidance to produce a Best Practice on Collision Avoidance | 2020, 28 Jan, IS: Lead scott.leonard@noaa.gov, EUM: andrew.monham@eumetsat.int, PierLuigi.Righetti@eumetsat.int No progress yet | CGMS-48 | OPEN
EUM | WGI/7.1 | WGI/A47.10 | Perform a detailed analysis consisting of: • Developing a simulation algorithm considering all variables affecting the LEO Orbit coordination • Developing plots and other simulation outputs as tools for illustrating the potential coordination possibilities and improvements in both global and direct broadcast mission return in a cross-member coordinated mission analysis approach. | 2020, 28 Jan, WGI IS: Inital similations performed by EUM, progress will be reported at CGMS-48 | CGMS-48 | OPEN
WGI | WGI/7.1 | WGI/A47.11 | Develop a Best Practice on the considerations to be made on orbital phasing between satellites, as a measure for reducing pass scheduling conflicts and maximising the amount of instrument observation collected. | 2020, 28 Jan, WGI IS: No progress so far, awaiting completion of A47.10 | CGMS-48 | OPEN
CGMS-47 WGI Recommendations
Lead | AGN item | Rec # | Description | Recommendation feedback/closing document | HLPP ref
CGMS members | WGI/3.1 | WGI/R47.01 | CGMS members are recommended to take appropriate actions towards their national frequency regulatory authorities to support unwanted emission limits for IMT-2020/5G at 26 GHz in the order of -42 dB(W/200 MHz) for base stations and -38 dB(W/200 MHz) for terminal stations to protect passive sensors in the 23.6 – 24 GHz band. | COMPLETED 2020, 28 Jan, IS: Closed following WRC-19
CGMS members | WGI/3.1 | WGI/R47.02 | CGMS members are therefore are recommended to propose to their national frequency regulatory authorities not to support an identification for IMT-2020/5G in the bands 47.2-50.2 GHz and 50.4-52.6 GHz in order to protect passive sensors in the neighbouring passive bands 50.2-50.4 GHz and 52.6-54.25 GHz. | COMPLETED 2020, 28 Jan, IS: Closed following WRC-19

## CGMS-47 WGII
WGII actions open from previous plenary sessions (at CGMS-47)
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
IROWG | 4 | A45.02 | IROWG to develop a detailed proposal for OSSEs regarding LEO-LEO MW occultation and GNSS-RO&-reflectometry. | 2020 12 March WGII IS #2: Reflectrometry already flying. The rest is pending depending on such missions flying. Report to CGMS-48? 2020 Jan 9 WGII IS #1: Ongoing for GNSS-RO-reflectometry, open for LEO-LEO MW. (U. Foelsche) CGMS-47: Pending IROWG meeting autumn 2019 WGII IS#2 2019: Next update expected at next IROWG meeting in September 2019... WGII IS#1 Dec 2018: OSSE work to assimilate GNSS-R observations has already started in the context of the CYGNSS mission, but there is still work to be done. Regarding LEO-LEO: The critical missing link is to develop a LEO-LEO forward operator that can be used in NWP systems. Currently it is unclear who would be paying for such a development. Detailed status report on this action dated 6 June 2018 is available from IROWG (contact: ulrich.foelsche@uni-graz.at). CGMS-46: Action remains open following WGII discussions. WGII IS#2 15 Mar 2018: No progress information. 1 Feb 2018/29 Nov 2017: Activity initiated, IROWG has reached out to its members, deadline extended. Regarding the GNSS-R OSSEs, some work has been done to be extended as the global observing system develops. Regarding LEO-LEO occultation OSSEs, limited progress is expected prior to CGMS-46. | Sept 2019 (CGMS-47, 1 Nov 2017, CGMS-46) | ONGOING
IPWG | 4 | A45.04 | IPWG to produce documentation on precipitation climate data record generation and related activities worldwide, including prospects for continuity | 2020 Mar 6: IPWG-10 postponed 2020 Jan 9 WGII IS #1: Next opportunity to discuss will be IPWG-10 in June 2020. (R. Ferraro) CGMS-47: Ongoing. In conjunction with GEWEX, a precipitation assessment is underway and was discussed in detail at IPWG-9 through a dedicated session. The goal is to have the assessment completed in 2020. WGII IS#2 2019: IPWG engaged with SCOPE-CM, working closely with GEWEX. Proposed to be closed at CGM-47 due to progress as follows (Ralph Ferraro will make presentation): 1. IPWG maintains updated information on its web page regarding CDR quality data sets (and solicits this from its members). See http://www.isac.cnr.it/~ipwg/data.html This is done in concert with other groups such as CEOS, GEWEX, etc. 2. For the recommendation, this is where our precipitation assessment comes into play. One of our past co-chairs, Remy Roca, leads the GEWEX Data Working Group, and Remy, along with outgoing co-chair, Ziad Haddad, organized a precipitation assessment. WGII IS#1 Dec 2018: At IPWG-9 (in Nov 2018) updates were given on the joint precipitation work with GEWEX. Goal is to have this assessment completed by the end of next year (2019). ECV gap analysis on this theme led to a coordinated action to be considered by IPWG, CEOS PCVC and SCOPE-CM (coordinated action within JWG Climate). CGMS-46: Action remains open following WGII discussions. WGII IS#2 15 Mar 2018: ECV gap analysis on precipitation CDRs ongoing with involvemetn from IPWG. Part of IPWG report to CGMS-46. 7 Mar 2018: In conjunction with GEWEX, a precipitation assessment is being planned; a mature outline, with associated section leads, have been identified and will be discussed further over the coming months and at IPWG-9. WGII IS #1 20 Nov 2017: IPWG is organsing a precipitation assessment jointly with GEWEX - with a kick off meeting held in Oct. 2017. Co-Chair Haddad and former co-chair Roca (who serves as lead of the GEWEX Data Working Group) are co-organisers. | CGMS-48 (CGMS-47, -46) | OPEN
CGMS agencies | 4 | A45.06 | CGMS Agencies to implement Landing Pages on calibration events accessed via WMO-OSCAR. | 2020 Jan 9 WGII IS #1: Status of Landing pages • Reports were expected from 9 agencies: CMA, ESA, EUMETSAT, IMD/ISRO, JMA, KMA, NASA, NOAA andRosHydroMet; • Reports are available from 7 agencies: CMA, ESA, EUMETSAT, JMA, KMA, NOAA and RosHydroMet; • GSICS intercalibration practices have been reported by 5 agencies: CMA, EUMETSAT, JMA, KMA andRosHydroMet. The Landing pages whose links have been so far received and recorded in OSCAR/Space comply with the expected contents to a variable extent, depending on the agency. The most frequent type of non-compliance is the lack of coverage of some of the items supposed to be handled (it should be noted that some of the Landing pages are still under development at the responsible agency). Other frequent problems are clarity, and balancement of the level of detail across the various sections. IMD and NASA are still expected to provide their Landing Pages. (B.Bizzarro, H.Pohjola) CGMS-47: See CGMS-47-WMO-WP-15 for status update. Some agencies still to provide landing page information. WGII IS#1 Dec 2018: Ongoing - WMO is in the process of updating/implementing missing Landing Pages. EUMETSAT and the CGMS Secretariat will verify the CGMS agencies landing pages in OSCAR. Sep 2018: See also WGIII action A46.03 CGMS-46: Action remains open following WGII discussions. CGMS-46 WMO-WP-02 WGII IS#2 15 Mar 2018: Other agencies are requested to provide the URL to their respective landing pages. KMA implemented the Landing Pages on COMS calibration events on June 2016. http://nmsc.kma.go.kr/html/homepage/en/landing/info.do#coms IMD Dr. Ashim K. Mitra, Scientist-D (SR-Cal/Val) NASA charles.webb@nasa.gov NOAA mitch.goldberg@noaa.gov ROSH z.andreeva@meteorf.ru http://planet.rssi.ru/calval/portal-main-en (the web-page is under construction) | CGMS-48 (CGMS-47, -46) | OPEN
ITWG (CGMS members) | WGII/5 | A46.01 | CGMS members to provide a summary of their known unfilled spectroscopy needs, and to develop a means of facilitating interaction between laboratory spectroscopy groups to spur cooperation and mitigate the lack of resources (financial and persons). (Ref. CGMS-46-ITWG-WP-01) | 2020 Jan 9 WGII IS #1: Open CGMS-47: No update. Mitch to go back and discuss with ITWG. Presentation to be given to CGMS-48. WGII IS#2 2019: Ken/Mitch to check with CGMS-Secretariat if action has been taken to ask CGMS members to provide input. CGMS-47 EUM-WP-xx | CGMS-48 (By CGMS-47) | OPEN
CGMS members | WGII/5 | A46.02 | All AMV producers to implement the “Common QI module” in their algorithms. | 2020 Mar 12 WGII IS #2: Régis Borde (EUMETSAT, IWWG): JMA has completed the integration 2020 Jan 9 WGII IS #1: To be reviewed at the IWWG meeting in April 2020. (Régis Borde, Steve Wanzong) CGMS-47: Common QI showed skill in filtering collocated AMVs and led to improved agreement between AMVs generated by satellite operators • Action 1 to IWWG co-chairs: Place the Common QI in a public repository. • Done -> https://github.com/swanzong/IWWG • Send any questions to stevew@ssec.wisc.edu • Recommendation 1 to AMV producers: Implement the software prior to IWW15 • Partially complete : EUMETSAT and NWCSAF/HRW have included the Common QI in their repositories. NOAA, KMA and JMA have plans to complete the integration in late 2019. WGII IS#2 2019: Request to developers to implement this. On-going. WGII IS#1 Dec 2018: There is a Gitlab repository (who is the owner of it?), tested by a few people. An email needs to be sent out to the IWWG community asking them to add this to their software (Steve Wanzong, Co-Chair, IWWG) | By IWW15, CGMS-48 | OPEN
CGMS members | WGII/5 | A46.03 | AMV producers to adopt the new AMV BUFR template. | 2020 Mar 6: IWW15 postponed until 14-18 Sept 2020 Jan 9 WGII IS #1: To be reviewed at the IWWG meeting in April 2020. (Régis Borde, Steve Wanzong) CGMS-47: The AMV sequence 3.10.067 endorsed by the WMO in November 2017 has been rejected by some users in early 2018 because it could not be used in automated framework. • The WMO corrected the sequence appropriately and endorsed the new AMV BUFR sequence 3.10.077 in November 2018. • NOAA, EUMETSAT and JMA are working on the production of the test data, planning an operational change early 2020. The NWCSAF will release a software patch later in 2019 which includes the new BUFR sequence. A new deadline to IWW15 (spring 2020) has been set to agencies to change their AMV BUFR sequence. • AMV producers to provide their users with a small test dataset (a few hours of data) encoded in the new BUFR format as soon as possible. • Nine months later, AMV producers will provide parallel dissemination of their AMV data in the new and old BUFR sequence over a 2-3 month period of time to allow the switch to take place. | End 2019 | OPEN
NWP community | WGII/5 | A46.04 | NWP community to define the best configuration to be used by the AMV producers, for use in global and regional NWP models. | 2020 Mar 6: IWW15 postponed until 14-18 Sept 2020 Jan 9 WGII IS #1: To be reviewed at the IWWG meeting in April 2020. (Régis Borde, Steve Wanzong) CGMS-47: The Met Office and Met Norway is planning to test various configurations of AMVs, via the NWC SAF software, to work towards optimal configurations. • There are no updates to report at this time. • We expect more discussion at the IWW15. • No results to report yet. • This topic and results will be re-visited at IWW15. WGII IS#1 Dec 2018: The two NWP contacts that will help with this action are: Mary Forsythe mary.forsythe@metoffice.gov.uk and Roger Randriamampianina rogerr@met.no (Steve Wanzong, Co-Chair, IWWG) | By IWW15, CGMS-48 | OPEN
IWWG | WGII/5 | A46.06 | IWWG to look at improving quality indicators for high resolution wind derivation for mesoscale and regional applications. (Ref. CGMS-46-IWWG-WP-01) | 2020 Mar 6: IWW15 postponed until 14-18 Sept 2020 Jan 9 WGII IS #1: To be reviewed at the IWWG meeting in April 2020. (Régis Borde, Steve Wanzong) CGMS-47: Research activities continue that aim to identify additional quality information from the AMV derivation that could be used to filter out poor quality AMVs and/or set observation errors for the AMV height assignment. • Quality measure associated with the correlation surface (addresses feature tracking) • Optimal estimation cost associated with cloud top temperature retrieval (addresses AMV height assignment) • Cloud top pressure error estimates (addresses AMV height assignment) • No results to report at this time. • We expect that some useful information relevant to this action may be extracted from work associated with A46.04. • This topic will be re-visited at IWW15. WGII IS#2 2019: no update | CGMS-48 (By CGMS-47) | OPEN
IWWG | WGII/5 | A46.07 | IWWG to consider developing climate projects from Atmospheric Motion Vectors (AMVs) and to report to the CEOS/CGMS WGClimate with a potential pilot project. (Ref. CGMS-46-IWWG-WP-01) | 2020 Mar 6: IWW15 postponed until 14-18 Sept 2020 Jan 9 WGII IS #1: To be reviewed at the IWWG meeting in April 2020. (Régis Borde, Steve Wanzong) CGMS-47: IWWG has reviewed the gaps identified by the last Essential Climate Variables (ECV) inventory. • The international status of polar and geostationary AMV reprocessing has been updated and is presented in Annexe 1 of the IWWG Working Paper. • This topic will be discussed in a specific session at the next at IWW15. WGII IS#2 2019: no update | CGMS-48 (By CGMS-47) | OPEN
IROWG | WGII/5 | A46.08 | IROWG to develop process and principles for RO data quality control to ease intercomparison of data from different providers. | 2020 Mar 12 WGII IS #2: Included in the IROWG-7 workshop outcome report. Ulrich Foelsche, IROWG: * Estimated 10-30% rejected for some of the current missions, Expected and actual satellites, orbits, space sampling/inhomogeneous flag, neutral/space * Action: Data providers to document data processing QC processes (including a month of QC statistics, e.g. rejection percentage at each QC step) and space sampling information and provide to IROWG. 2020 Jan 9 WGII IS #1: First results will be included in the report of IROWG-7 Meeting of September 2019. (U. Foelsche) WGII IS#2 2019: to be raised at next IROWG in September 2019. 10 Oct 2018: Best practices to be developed. (WGII to consider extension to other areas e.g. winds/IWWG). To be raised at the next IROWG meeting (date TBD) | CGMS-48? Sep 2019 | OPEN
CGMS members | WGII/7 | A46.13 | CGMS members to provide comments on the impact studies conducted by ECMWF on OSES vs. FSOI and how CGMS members can benefit from the findings. (Ref. CGMS-46-WMO-WP-13 and WP-13_PPT) | 2020 Mar 6: ECMWF would like to close this action. The guidance has been given and remains. WGII to discuss on how to take this onboard. 2020 Feb 12 WMO-ECMWF discussion: ECMWF provided guidance to CGMS space agencies on how to interpret and present the FSOI stats in CGMS-46 WMO-WP-13. CGMS members are requested to note and follow these guidelines. ECMWF is ready to provide more guidance to CGMS members as necessary. To be discussed at CGMS-48 2020 Jan 9 WGII IS #1: - | CGMS-48? (CGMS-47) | OPEN
CGMS members | WGII/10 | A46.14 | CGMS members to provide points of contact for GOFC-GOLD to the CGMS Secretariat (Ref. CGMS-46-GUEST-WP-02) | 2020 Mar 12 WGII IS #2: CGMS members to provide pocs. CGMS members interested are invited to attend meetings of these groups. NOAA is involved. Meetings to be added to the CGMS online calendar. NASA: ? NOAA: ? 2020 Jan 9 WGII IS #1: - CGMS-47: WGII to reach out to GOFC-GOLD. | By 31 August 2019 | OPEN
CGMS members | WGII/10 | A46.15 | CGMS members to provide points of contact for AEROSAT to the CGMS Secretariat (Ref. CGMS-46-GUEST-WP-01) | 2020 Mar 12 WGII IS #2: CGMS members to provide pocs. CGMS members interested are invited to attend meetings of these groups. NOAA is involved. Meetings to be added to the CGMS online calendar. NASA: ? NOAA: ? 2020 Jan 9 WGII IS #1: - CGMS-47: WGII to reach out to GOFC-GOLD. | By 31 August 2019 | OPEN
CGMS-47 WGII actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
GSICS | WGII/4 | A47.01 | GSICS to expand GSICS Report on the State of the Observing System to successively cover the calibration status of all instruments relevant GSICS. | 2020 Mar 6; GSCIS and GSCIS EP meetings postponed. Teleconferences expected for the WGs, first one on Tue 17 March. Face2face meetings likely to take place next year. 2020 Jan 9 WGII IS #1: To be reviewed by GSICS meeting in March 2020. (M. Goldberg) | CGMS-48 | OPEN
WMO | WGII/4 | A47.02 | WMO to remove current formulation of ‘GSICS calibration’ and to rename 'calibration and events' to ‘instrument landing page’ | 2020 Jan 9 WGII IS #1: WMO has implemented this. | Dec 2019 | CLOSED
CGMS Agencies | WGII/4 | A47.03 | Agencies assessing commercial radio occultation data are requested to present their efforts at IROWG-7 to facilitate community planning. | 2020 Jan 9 WGII IS #1: Presented at IROWG-7. (U. Foelsche) | Sep 2019 | CLOSED
IROWG | WGII/4 | A47.04 | IROWG to provide recommendation on orbital planes in order to improve coverage. | 2020 Jan 9 WGII IS #1: Discussed at IROWG-7 and will be reflected in meeting report. (U. Foelsche) | Sep 2019, CGMS-48 | CLOSED
IROWG | WGII/4 | A47.05 | IROWG to evaluate outcome of Agency funded commercial weather data pilot following IROWG-7 and report back to CGMS-48. | For closure? 2020 Mar 12 WGII IS #2: IROWG can only respond to this action if the missions are flown. 2020 Jan 9 WGII IS #1: Evaluation reports are not publicly shared and therefore prevent evaluation by IROWG at this time. (U. Foelsche) | CGMS-48 | OPEN
ROSH | WGII/4 | A47.06 | Roshydromet to report on future plans for RO missions at WG II. | 2020 Jan 9 WGII IS #1/12 Mar #2: No further information available | CGMS-48 | OPEN
WGII | WGII/4 | A47.07 | WGII to discuss with WMO the way forward to have access to telecommunications microwave link data in support of IPWG validation activities. | 2020 Mar 12 WGII IS #2: Narrative was provided to WMO on 12 March 2020. WMO connected IPWG to the chair of the WMO Steering Group on Radio Frequency Coordination (SG-RFC), Mr. Eric Allaix, to see if SG-RFC can provide advice on a way forward. 2020 Mar 6: IPWG-10 has been postponed, should this matter be adressed at that meeting. 2020 Jan 9 WGII IS #1: IPWG will provide more specific information to WMO on what is actually required, so that WMO can act upon this request. (R. Ferraro) | CGMS-48 | OPEN
SCOPE-CM | WGII/4 | A47.08 | SCOPE-CM to report back on the conclusion of the 9 pilot projects | 2020 Mar 12 WGII IS #2: WMO to report in May 2020 2020 Mar 6: Changes with SCOPE-CM ongoing? Chair stepping down? 2020 Jan 9 WGII IS #1: No further information available | CGMS-48 | OPEN
SCOPE-CM | WGII/4 | A47.09 | SCOPE-CM to provide an implementation plan based on the agreed new concept including an agenda and updated ToRs. | 2020 Mar 12 WGII IS #2: WMO to report in May 2020 2020 Mar 6: Changes with SCOPE-CM ongoing? Chair stepping down? 2020 Jan 9 WGII IS #1: No further information available This is also a plenary action A47.15. | CGMS-48 | OPEN
CGMS Agencies | WGII/4 | A47.10 | Agencies to continue to support the WMO maintained trust-fund that enables the work of the VLAB technical officer and report to CGMS-48 | 2020 Jan 9 WGII IS #1: CGMS agencies in addition to EUMETSAT, NOAA and KMA are invited to contribute to the Vlab Trust Fund. Please contact Werner Balogh at wbalogh@wmo.int. | CGMS-48 | OPEN
CGMA Agencies | WGII/4 | A47.11 | Agencies to endorse the VLAB 5-year strategy plan. | Endorsed by CGMS-47 plenary. | CGMS-47 (CGMS-46) | CLOSED
CGMS and VLAB | WGII/4 | A47.12 | Agencies to provide links to their training events and resources for VLAB communication. | 2020 Jan 9 WGII IS #1: CGMS agencies to follow-up on this action. Please send links to VLab Techncial Support Officer Ms. Luciane Veeck (Luciane Veeck <luveeck@googlemail.com>). | Dec 2019 | OPEN
CGMS Agencies | WGII/4 | A47.13 | Agencies to provide nominees for next VLAB co-chair starting in 2020 for three years. | 2020 Mar 12 WGII IS #2: Still no nominations 2020 Jan 9 WGII IS #1: To date no nominations have been received. This is also a plenary action. | Dec 2019 | OPEN
WGIII | WGII/5 | A47.14 | WGIII to provide their assessment and planning for the next risk assessment to the ISWGs, JWGClimate and GSICS. | 2020 Mar 12 WGII IS #2: To be addressed in CGMS-48 WGII and WGII-WGIII joint session in particular. CGMSSEC will circulate the baseline and risk assessment as soon as finalised. 2020 Feb 19: Adressed at the 2nd CGMS risk assessment WS 19-21 Feb 2020. Risk assessment document to be shared with CGMS. Included in WGIII LOA | Mar/Apr 2019 | OPEN
IROWG, ICWG, IWWG, IPWG, ITWG, GSICS, WGClim | WGII/5 | A47.15 | The ISWGs, WGClimate and GSICS to review WGIII Risk assessment and consider mitigation opportunities. | 2020 Feb 19: The outcome of the 2nd CGMS risk assessment WS 19-21 Feb 2020 to be distributed to the ISWGs, GSICS And WGClimate | CGMS-48 | OPEN
ICWG | WGII/7 | A47.16 | ICWG to organise a dedicated session (0.5-1 day) on lightning observations from space (calval, algos, applications and products) | 2020 Mar 12 WGII IS #2: Progress ongoing. Once meeting held, ICWG expects to close the action. 2020 Jan 9 WGII IS #1: Session will take place at next ICWG meeting in September 2020. ICWG to report on session planning at CGMS-48. | CGMS-48 (Dec 2019) | OPEN
CGMS space agencies | WGII/8 | A47.17 | CGMS agencies encouraged to present papers at CGMS-48 on use of satellite products for agricultural applications (ref CGMS-47-WMO-WP-11) | 2020 Jan 9 WGII IS #1: included in CGMS-48 WG II agenda. CGMS agencies invited to present relevant topical papers. New action following WGII report preparation | CGMS-48 | OPEN
EUMETSAT | WGII/8 | A47.18 | EUMETSAT to provide PoC for NOAA for OSI SAF for discussion on future collaborative work/workshop for development of cryospheric products. | NOAA informed 28 Oct 2019 (E-mail A Taube-M Butler) Cécile Hernandez Météo-France, Centre de Métérologie Spatiale, av Lorraine, BP 50747, 22307 Lannion cedex, France Phone: +33 296 056 796 Fax: +33 296 056 737 cecile.hernandez@meteo.fr | Oct 2019 | CLOSED
CGMS space agencies | WGII/8 | A47.19 | CGMS agencies to present solutions at CGMS-48 for satellite-based bathymetry (CGMS-47-WMO-WP-13) | 2020 Mar 12 WGII IS #2: WMO tropical cyclone programme, users are looking for satellite based bathymetry. 2020 Jan 9 WGII IS #1: - New action following WGII report preparation | CGMS-48 | OPEN
CMA | WGII/8 | A47.20 | CMA to provide information on ILS and SRF and other relevant documentation to the user community for the development of necessary RTMs/tools for the exploitation of HIRAS and GIIRS data. (Reference: Action (SG3.22) from the NWP SAF Steering Group) | 2020 Jan 9 WGII IS #1: Information has been provided. (K. Holmlund) | Dec 2019 | CLOSED
GSICS, WGClim, SCOPE-CM | WGII/8 | A47.21 | GSICS, WGClimate and SCOPE-CM to organise a workshop on calibration supporting reprocessing. | 2020 Mar 12 WGII IS #2: To be discussed on 17 March within GSICS community. 2020 Jan 9 WGII IS #1: - (First review to take place at GSICS meeting in March 2020, Korea - meeting cancelled). | Mar 2020, CGMS-48 | OPEN
NOAA/ CMA | WGII/10 | A47.22 | NOAA/CMA to provide final report from the flood mapping pilot for CGMS-48. | 2020 Mar 12 WGII IS #2: Report to CGMS-48. There will be a CEOS flood pilot project 2020 Jan 9 WGII IS #1: - | CGMS-48 | OPEN
SWCG | WGII/11 | A47.23 | SWCG to further develop white-paper on current instruments and their calibration and to provide report to GSICS for review | 2020 Jan 9 WGII IS #1: M. Goldberg to follow up with SWCG. | Dec 2019 | OPEN
GSICS | WGII/11 | A47.24 | GSICS to review SWCG white-paper on calibration and consider opportunities for GSICS support to aforementioned activity. | 2020 Jan 9 WGII IS #1: M. Goldberg to follow up with SWCG. | Mar 2020 | OPEN
WG II | WGII/12 | A47.25 | WG II to review its terms of references during intersessional meetings before CGMS-48. | 2020 Jan 9 WGII IS #1: - | Nov 2019, Mar 2020 | OPEN
JMA | WGII/13 | A47.26 | JMA to coordinate with related parties and close down the JMA Volcanic Ash algorithm Testbed. | 2020 Jan 9 WGII IS #1: JMA inquired any question or comment about the JMA Testbed closing down with the end of last year as a deadline. There were no questions or objections on the closing. | CGMS-48 | CLOSED
CMA | WGII/13? | A47.27 | CMA to provide a PoC for the IPWG validation protocol (HLPP 4.3.1) | 2020 Mar 12 WGII IS #2: Open 2020 Jan 9 WGII IS #1: No name provided yet to IPWG. (R. Ferraro) (included in the IPWG report section) | Dec 2019 | OPEN
WMO | WGII/14 | A47.28 | WMO to provide a preliminary report from the 7th WMO Impact Workshop (Seoul, May 12-15 2020) at CGMS-48 | 2020 Mar 12 WGII IS #2: TBD if workshop will be held. 2020 Jan 9 WGII IS #1: - New action following CMGSSEC review 27 May 2019 (following input by WMO). | CGMS-48 | OPEN
GSICS | from WGIII | A47.29 | GSICS to continue cross calibration progress of microwave imagers. (WGII) | 2020 Mar 12 WGII IS #2: 2020 Jan 9 WGII IS #1: To be reported at next annual GSICS EP meeting in May 2020. New action requested by WGIII | CGMS-48 | OPEN
ESA | WGII/9 | A47.30 | ESA to present a paper on SAR applications for storms and flooding with information on enhanced acquisitions and latency. (ref CGMS-47 WMO-WP-12) | 2020 Jan 9 WGII IS #1: Included in CGMS-48 WGII agenda New action following WGII report preparation | CGMS-48 | OPEN
IROWG, WMO | WGII/4 (from WGIII) | A47.31 | CGMS baseline and RO: IROWG and 7th WMO Impact Workshop needs to validate the current Baseline requirements in terms of the coverage, number, quality and sampling of RO. | 2020 Mar 6: Unclear if the impact workshop will be held/postponed. 2020 Feb 19: Pending the 7th impact WS. Dedicated telecon held with IROWG. 2020 Jan 9 WGII IS #1: - CGMS-47: Action from WGIII to WGII Added as action | 2020, CGMS-48 | OPEN
IROWG | WGII/4 (from WGIII) | A47.32 | IROWG to review the CGMS Baseline and validate wording that captures CGMS Member contribution to RO data in terms of coverage, number, quality and sampling; and share impact studies of RO data between the CGMS Baseline and WIGOS 2040 vision observing targets. | 2020 Feb 19: The outcome of the 2nd CGMS risk assessment WS 19-21 Feb 2020 to be distributed to the ISWGs, GSICS And WGClimate 2020 Jan 9 WGII IS #1: - CGMS-47: Action from WGIII to WGII Added as action | 2019/ 2020 | OPEN
CGMS-47 WGII Recommendations
Lead | AGN item | Rec # | Description | Recommendation feedback/conclusions | HLPP ref
ISWG Chairs | WGII/3 | WGII/R47.01 | ISWG Chairs to organise intersessional teleconferences amongst the co-chairs.
CGMS members | WGII/4 | WGII/R47.02 | From ICWG: CGMS members to budget a baseline funding for the intercomparison study, given its importance and impacts on global cloud products. | NB This is also marked as a plenary recommendation.
CGMS | WGII/4 | WGII/R47.03 | From ICWG: CGMS members to consider introducing multi-sensor (satellite and ground-based measurements) applications for convective nowcasting when developing/updating product requirements. | NB This is also marked as a plenary recommendation.
ICWG, IWWG | WGII/4 | WGII/R47.04 | ICWG and IWWG: ICWG to work with IWWG on the golden days observations to provide cloud height uncertainty for AMV applications
CGMS | WGII/4 | WGII/R47.05 | From ICWG: CGMS agencies to continue operating conically-scanning passive MW sensors in an early afternoon orbit as well as in a dusk/dawn orbit in order to maintain this unique long-term time series. Progress was made in the interaction of the ICWG | NB This is also marked as a plenary recommendation.
WGII | WGII/4 | WGII/R47.06 | WGII recommends to Plenary the endorsement of the proposed new concept for SCOPE-CM. | COMPLETED. Endorsed by CGMS-47 plenary.
CGMS | WGII/4 | WGII/R47.07 | WGII recommends to Plenary the proposed approach for Leadership in WGClimate | COMPLETED. Endorsed by CGMS-47 plenary.
CGMS | WGII/4 | WGII/R47.08 | WGII recommends to Pleanry the adoption of the updated WGClimate ToRs | COMPLETED. Endorsed by CGMS-47 plenary.
CGMS | WGII/4 | WGII/R47.09 | WGII recommends to Plenary the inclusion of Greenhouse Gas Monitoring activities in WGClimate as presented in CGMS-47-JWGCLIM-WP-03WGII | COMPLETED. Endorsed by CGMS-47 plenary.
ESA and EC | WGII/8 | WGII/R47.10 | ESA and EC to explore the possibility of creating a European service (or a component within an existing service) to optimize SAR acquisitions over TCs, and to provide, in near real time, the SAR observations and surface wind field estimates to the Tropical Cyclone community at large, both with data formats
ISRO | WGII/9 | WGII/R47.11 | ISRO is encouraged to consider follow-on missions on scatterometry to Oceansat-3/3A
CMA | WGII/14 | WGII/R47.12 | CMA is encouraged to present their impact analysis work at the upcoming WMO NWP Impact Workshop in May 2020.
CGMS members | WGII/5 | R46.02 | CGMS member are encouraged to take due consideration to climate applications requirements during the planning for new meteorological satellite missions. (Ref. CGMS-46-ITWG-WP-01) | CGMS-47: ICWG invited IPWG representative Ben Johnson to present at ICWG-2 and engagement is developing. WGII IS#2 2019: needs to be further precised/developed (GCOS?, FCDR). Possibly with WGClimate? WGII IS#1 Dec 2018: WGII co-chairs to check with Mitch Goldberg Sep 2018 CGMSSEC: WGII is requested to make this more specific.
ISRO | 7 | R45.07 | ISRO to consider adding a direct broadcast capability to future satellites. | CGMS-47: recommendation maintained
CGMS agencies | 8 | R45.09 | CGMS agencies encouraged to document their products online, including ATBDs and validation reports, and link product page URLs to the WMO Product Access Guide following defined documentation criteria. (current agency focal points in WMO IPET-SUP: Sally Wannop (EUMETSAT), Natalia Donoho (NOAA), Geun-Hyeok Ryu (was Chu-Yong Chung) and Jin Woo (KMA), Xiang Fang (CMA), Shiro Ohmori (JMA)) | CGMS-47: Ongoing. For NOAA: NOAA-WP-16 (Landing pages include this information). WGII IS#1 Dec 2018: To be addressed in IPET-SUP-5 in February 2019. WGII IS#2 15 Mar 2018: WMO has taken these into account. KMA has registered a link to COMS L1B imagery in 2015 for WMO PAG and is currently available. KMA’s renewed web page has been setup including MI level 2 products image and ATBD. KMA is preparing its registration process for PAG. -MI Level 2 products image http://nmsc.kma.go.kr/html/homepage/en/ver2/satellites/coms/searchSatelliteImageN.do?data_type=1089 -MI Level 2 products ATBD http://nmsc.kma.go.kr/html/homepage/en/ver2/common_board/Data/selectData.do?board_c_cd=023&cmn_data_seq_n=5322 KMA POC - Geun-Hyeok Ryu (geunhyeokryu@korea.kr) - Jin Woo (superjwoo@korea.kr) IMD will prepare an online product document including ATBD, validation report and its link will be communicated to WMO product access guide.
CGMS members | WGII/4 | R44.05 | CGMS members to budget a baseline funding for the cloud intercomparison study, given its importance and impacts on global cloud products. | CGMS-47: Addressed in WGII and plenary. WGII IS#1 Dec 2018: Discussed at the ICWG . Message to remain. IWWG side funded. ICWG not yet. WGII IS#2 15 Mar 2018: For further discussion within ICWG. Co-chair to provide an update. CGMS-45: ICWG-WP-01: Currently, ICWG helps to facilitate the collection of data used for assessments (e.g., level-2 retrieval assessment in TG “Assessment of level-2 retrievals” or level-3 climate data records in TG “Assessment of cloud parameter data records for climate studies”), but many teams carried out the efforts on a volunteer basis. Lack of funding has limited the scope and prohibited a definitive analysis of the new HIMAWARI-8 data set.
CGMS R&D agencies | WGII/4 | R44.07 | Research agencies to consider continuing space-borne lidar for ice/liquid water since they have proven very valuable to validate retrievals from passive sensors | CGMS-47: recommendation maintained WGII IS#2 15 Mar 2018: Maintain it as a recommendation. US decadal survey on EO from space, specific measurements were noted , will influence the decision making.
CGMS space agencies | WGII/4 | R44.15 | Future satellite programmes should include the provision of high temporal frequency MW humidity sounding radiances (alongside cloud and precipitation sensitive observations). | CGMS-47: not part of the CGMS baseline. Monitor progress, in particular with regards to small satellites. WGII IS#2 2019: Check if discussed in WG III Risk Assessment Workshop. Mails have been sent to WGIII co-chairs/rapporteur to check. WGII IS#1 Dec 2018: WGII co-chairs to contact WGIII co-chairs and the pass recommendation to WGIII. Sep 2018 CGMSSEC: Suggest this is an action on WGIII for consideration. CGMS-45: NASA Cubesat mission Tropics underway CGMS-44 WGII - For reference: WG III should discuss this and come up with results at CGMS-45.
ROSC, ROSH | WGII/4 | R44.16 | Roscosmos to develop and release a direct broadcast processing package (for level 1 data) for the MTVZA-GY microwave imager. Roshydromet to provide dissemination of this package to interested users. | CGMS-47: recommendation maintained WGII IS#1 Dec 2018: Letters have been sent (by whom?) Apr 2018: Following feedback from Roshydromet, the text of this recommendation has been updated (as discussed during CGMS-45 WGII).
CGMS space agencies | WGII/4 | R44.18 | CGMS satellite operators to consider coordination of orbits for scatterometer instruments and to provide open and timely access to data in order to maximise independent coverage and benefits to nowcasting and NWP from assimilation of scatterometer wind data. | 2020 Feb 19: It was proposed to capture this recommendation within the scope of the HLPP (CGMSSEC to prepare draft text) CGMS-47: Proposed to be transferred to WG III. Following further discussion in the CGMS Secretariat, we propose that this recommendation is maintained in WGII until CGMS-47, and then taken up when the risk assessment is discussed, at that stage we can see if it should be transferred to WGIII (or stay in WGII). WG II IS#2 2019: Mails have been sent to WGI co-chairs/rapporteur to transfer this recommendation to WG I. WGII IS#1 Dec 2018: WGII co-chairs to contact WGI co-chairs to forward recommendation to WGI. Sep 2018 CGMSSEC: Suggests this is an action on WGI to consider coordination of orbits. CGMS-44 WGII - For reference: WG III should discuss this and come up with results at CGMS-45.
CGMS space agencies | WGII/6 | R44.21 | Operators to take into account in the planning of their data distribution systems the emerging stringent requirements on data latency from SRNWP | CGMS-47: maintain recommendation WGII IS#2 15 Mar 2018:
CGMS space agencies | WGII/7 | R44.25 | For monitoring the Polar Regions, the Group stressed the importance of the deployment of HEO missions | CGMS-47: NOAA considering in its system studies and talking with potential partners. WGII IS#1 Dec 2018: Meeting on 5 Dec 2018 at EUMETSAT to discuss HEO missions. Sep 2018 CGMSSEC: This recommendation needs rephrasing/formulation, closing or other. Link to WGIII required
CGMS space agencies | WGII/8 | R44.26 | Satellite operating agencies should support proposals and programs to acquire high-accuracy characterization measurements of the Moon, to develop a new, high accuracy, SI-traceable lunar reference standard for reflected solar wavelengths. | CGMS-47: Maintain 10 Apr 2019: Tom Stone who is the leader of lunar calibration in GSICS VINIR subgroup provided feedback see at end of this table. WGII IS#1 Dec 2018: KMA (Dohyeong Kim) to check with GSICS. WGII IS#2 15 Mar 2018: Update expected at the March '18 GSICS meeting. SWTT is preparig a proposal on integrating space weather products into GSICS. To be discussed at CGMS-46. CGMS-45: GSICS discussed this issue
CGMS space agencies | WGII/8 | R44.28 | Agencies to explore the possibilities to develop suitable processing packages to support a direct broadcast implementation of RO processing, within the DBNet to improve timeliness for space weather applications | CGMS-47: Recommended to be transferred to WG I. WGII IS#1 Dec 2018: To be maintained (See also CGMS-44 WGI action A44.08 related to IROWG)
CGMS members | WGII/3 | R43.02 | CGMS members to consider removing spectral gaps from future hyperspectral sounders to support GSICS intercalibration of IR imagers. | 2020 Feb 19: It was agreed that this recommendation shall be led by WGII. It could be addressed within the framework of WGII&WGIII discussions at CGMS-48. CGMS-47: recommendation maintained WGII IS#2 15 Mar 2018 To be discussed at second WGII inter-sessional meeting after CGMS-44. (For WG III to consider)
CGMS members | WGII/6 | R43.03 | CGMS members to consider include a water vapour channel and a CO2 channel to polar-orbiting imagers, to maintain accuracy and coverage of polar winds and cloud height retrievals achieved by MODIS. | CGMS-47: recommendation maintained WGII IS#2 15 Mar 2018: Maintain it as a recommendation. To be discussed at a second WGII inter-sessional meeting after CGMS-44. (For WG III to consider)
ISRO | WGII/5 | R43.10 | ISRO is encouraged to implement a multi-sensor precipitation estimate based on SAPHIR and INSAT-3D | CGMS-47: ISRO has carried out following activities: (1) Using Bayesian formulations, a new rain retrieval algorithm for SAPHIR is developed. (2) This algorithm is recently made operational on MOSDAC. (3) This is being used for merging the SAPHIR rain with INSAT measurements. INSAT-3D/3DR based Hydero-Estimator algorithm that provides pixel-scale and half-hourly precipitation is already operational. We will likely to complete the merging of precipitation from SAPHIR and INSAT-3D in near future. This recommendation may be kept open. WGII IS#2 15 Mar 2018: ISRO/IMD invited to report on this at CGMS-46. Nov 2017: IMD will coordinate with SAC (ISRO) to develop and implement the multi sensor precipitation estimate based on SAPHIR and INSAT-3D/3DR data on priority. CGMS-45: ISRO/IMD have plans
2019 April 10, Tom Stone who is the leader of lunar calibration in GSICS VINIR subgroup: There are several projects being conducted by satellite operating agencies and GSICS member institutions to acquire high-accuracy lunar measurements, eventually to redevelop the lunar calibration reference. * LUSI (NIST) The LUnar Spectral Irradiance (LUSI) project is ongoing by the U.S. National Institute of Standards and Technology (NIST). LUSI will acquire a long-term set of ground-based Moon observations from Mauna Loa Observatory (MLO) in Hawaii, USA (3402 m altitude). The LUSI instrument makes spectral measurements of the spatially integrated irradiance directly, with no spatial post-processing. Expected uncertainty is less than 1% absolute. The instrument calibration is traceable to NIST primary standards. Currently the instrument is being characterised and calibrated at NIST, and the MLO site is reserved and being prepared for installation of the LUSI observatory dome.
* air-LUSI (NASA, NIST, USGS) A smaller version of the NIST LUSI instrument has been developed for deployment on the NASA ER-2 high-altitude aircraft under a project sponsored by the NASA Earth Science Technology Office. The air-LUSI project is led by Kevin Turpie of the University of Maryland Baltimore County, in collaboration with the NIST LUSI team, the USGS lunar calibration project, and a robotics team from the University of Guelph, Canada. The experiment had a successful engineering flight in August 2018, reaching 21.3 km altitude; the lunar data currently are being processed. Science acquisition flights are scheduled for September 2019.
* Lunar measurement campaign (CMA) The China Meteorological Administration is continuing efforts to acquire measurements of the Moon using multiple different types of instruments, including imaging spectrometers, a hyperspectral lunar photometer, and a shortwave infrared Fourier Transform Spectrometer. Atmospheric characterisation instruments are operated alongside the lunar instruments. The CMA ground-based campaign has resumed at Lijiang (3193 m altitude), and another campaign is planned for Daocheng, Sichuan province.
* CLARREO Pathfinder (NASA) The Climate Absolute Radiance and Refractivity Observatory Pathfinder mission (CLARREO Pathfinder, CPF) will acquire views of the Moon with its Reflected Solar (RS) sensor as a demonstration of inter-calibration and measurement technologies. Science planning for lunar observations by CPF RS specifies capturing a wide range of phase angles when the Moon is observable from the instrument's location on the International Space Station. Presuming the lunar observations meet the absolute calibration goals for the RS sensor, the CPF Moon observations represent a potential to collect a substantial set of high accuracy lunar irradiance measurements. CLARREO Pathfinder is scheduled for launch to the International Space Station in early 2023.
* ARCSTONE (NASA) The ARCSTONE project will acquire lunar spectral measurements from a 6U cubesat platform, covering the wavelength range from 350 to 2500 nm. The instrument design allows observing the Sun and Moon through the same optical path with no interchange of components, thus giving a direct measure of lunar disk reflectance. Tying these measurements to the solar spectral irradiance, such as from the Total and Spectral Solar Irradiance Sensor (TSIS), can provide SI-traceable lunar spectral irradiance with potential sub-percent accuracy. The ARCSTONE project is funded by the NASA Earth Science Technology Office, and has a potential flight demonstration in the 2024 time frame.

## CGMS-47 WGIII
WGIII actions open from previous plenary sessions (at CGMS-47)
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
WGIII | WGIII/4.2 | A46.02 | WGIII to consider how to account for the unique SST conical microwave imager in the CGMS Baseline and Risk Assessment | 2020 19 Feb: Reviewed at the 2nd risk assessment WS on 19-21 Feb 2020. Baseline revision and risk assessment documents will be presented to CGMS-48 for endorsement. CGMS-48 CGMS-WP-10 and -12 CGMS-47: Adressed within the scope of the initial CGMS baseline and risk assessment performed in spring 2019. 1 Mar 2019: Discussed at the risk assessment workshop. As for the Baseline, these should be included once future plans are clearer. Future plans will be discussed at CGMS-47 plenary. WGIII IS #2 6 Feb 2019: No update. Topic to be discussed at the Risk Assessment Workshop Feb/Mar 2019. 24 Oct 2018 WGIII IS: To be discussed at risk analysis WS at EUMETSAT Feb/Mar 2019. Might consider feedback/ongoing discussions from related CEOS VCs. CGMSSEC/EUM: preparing a CGMS baseline document for publication on the CGMS website (as per CGMS-46) - to include the contingency plan? | CGMS-48 (CGMS-47) | OPEN
NOAA | F | A46.09 | On passive microwave observations: NOAA to inform CGMS on US's plans/frequency/ features of the post WindSat/SSMI MW radiometry missions (update on SSM/I) | CGMS-47: Transferred from plenary to WGIII. Deferred. Expected to be presented to CGMS-48. | CGMS-48 (CGMS-47) | OPEN
CGMS-47 WGIII actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
WMO | WGIII/4 | WGIII/A47.01 | Gap analysis, EGOS-IP/WOS-IP: WMO to report on the action it plans to undertake in response to the Vision for WIGOS in 2040 once it has been approved by the World Meteorological Congress (CGMS-47-WMO-WP-18: Update on WMO Gap Analysis and on status of EGOS-IP/WOS-IP) | 2020 Feb 19: Addressed at the 2nd CGMS WGIII risk assessment WS 2020 29 Jan, IS #1: WMO to report to CGMS-48 | CGMS-48 | OPEN
WMO | WGIII/5 | WGIII/A47.02 | Gap analysis and ISWG: WMO to conduct a Gap Analysis against the approved WIGOS Vision 2040 and to explore the possibility of coordinating this with the impact assessment planned by the CGMS Science Working Group reporting to WGII | 2020 Feb 19: WMO presented its document to the 2nd risk assessment workshop on 19-21 Feb 2020. 2020 29 Jan, IS #1: WMO to report to CGMS-48 To be addressed also at the 2nd risk assessment WS in Feb 2020 The HLPP or in a CGMS vision document, this might be highlighted | CGMS-48 | OPEN
WMO | WGIII/5 | WGIII/A47.03 | OSCAR/Space: WMO to hold a workshop on OSCAR/Space in order to develop plans for its sustainment and future development, both in terms of information content and system capability | 2020 Feb 19-21: 2nd CGMS WGIII risk assessment WS, WMO and EUMETSAT discussions ongoing. System capability is secured in the short to medium term. Long term is under discussion. 2020 29 Jan, IS #1: Pending implementation of WMO reform. Instructions included in guidelines for preparing CGMS working papers to be circulated by CGMSSEC. Workshop postponed pending WMO reform. | 2020 | OPEN
CGMS space agencies | WGIII/5 | WGIII/A47.04 | CGMS members and observers to provide updated information on the status of their satellites and instruments following the instructions and tables in CGMS-47 WMO-WP-17b | 2020 Feb 19: Ongoing, Members need to provide regular updates to WMO 2020 29 Jan, IS #1: Templates sent by WMO (to list of focal points). NOAA poc updated (from Matt Butler to Mary Ann Kutny). CGMSSEC to add list of pocs to this action. New action following WGIII report preparation | 2019-09-30 | OPEN
WMO | WGIII | WGIII/A47.05 | Noting the recent conclusions of the WMO IPET-DRMM and the concurrence expressed in CGMS WG III, WMO is encouraged to add the satellite identifier (from Common Code Table C5) and satellite instrument identifier (from Common Code Table C8) to OSCAR Space. (This action originates from WGIII discussions at CGMS-44, WGIII R44.02) | 2020 Feb 19: WMO now focuses on the NWP station identifiers. Action might be deferred to the future. (Changed from recommendation to action. CGMS-47 WGIII discussion). | CGMS-48 | OPEN
CGMS space agencies, O/SST members | WGIII/5 | A47.06a | The OSCAR/Space Support Team (O/SST) to continue providing information on their satellite programmes for accurate recording in OSCAR/Space, according to the recommended procedure with templates provided by the WMO Space Programme. Instructions and templates are available in working paper CGMS-47 WMO-WP-17b. | 2020 Feb 19: It was agreed to consolidate the actions (content and process) related to OSCAR/Space vis-à-vis the space agencies for further addressing at CGMS-48 (WMO to consolidate the actions, Space agencies to continue providing updates as requested). Introduced following the draft CGMS-47 report review by WMO. | 1 Dec 2019 | OPEN
CGMS space agencies, O/SST members | WGIII/5 | A47.06b | O/SST to review the table of "differentials" in the contents between OSCAR/Space and CEOS MIM database on satellite instruments. (The MIM team has provided the list of differentials information previously). | 2020 Feb 19: This exercise has been completed and is therefore closed. Introduced following the draft CGMS-47 report review by WMO. | 31 Aug 2019 | CLOSED
CGMS space agencies, O/SST members | WGIII/5 | A47.06c | CGMS members to participate in the OSCAR/Space database maintenance and evolution workshop to be organised by WMO prior to CGMS-48 | 2020 Feb 19: Refer to WGIIII action A47.06a Introduced following the draft CGMS-47 report review by WMO. | CGMS-48 | OPEN
WMO | WGIII/7 | WGIII/A47.07 | Early Morning Orbit: WMO to reconvene a WMO-CGMS Tiger Team on the impact of the Early Morning orbit. (It is currently premature to convene this Tiger Team until an assessment of FY-3E is conducted). | 2020 Feb 19: It is important to timely reconvene the Tiger Team to enable the team to start working shortly after the launch (and prior to declaring the s/c operational). Launch is tentatively scheduled for 2020/2021. Side discussions to be held on the sides of the upcoming 7th NWP impact workshop 11-15 May (if held) and/or on the sides of CGMS=48 WG meetings. CGMS-47/SWCG: The WMO CGMS Early Morning Tiger Team is requested to include space weather data in the impact analysis. | 2021 | OPEN
EUM | WGIII/7 | WGIII/A47.08 | GEO coverage in the IODC region: EUMETSAT to conduct a study on GEO Imager coverage, data quality, availability and resilience in the IODC region | 2020 Feb 19: EUMETSAT provided the status at the 2nd CGMS WGII risk assessment WS 19-21 Feb 2020 It is considered to be resilient. EUMETSAT will briefly address this at CGMS-48. (CGMS-48-EUMETSAT-WP-07) | CGMS-48 | OPEN |  | EUM: H/RSO and SEP/SSE, Preferred future sources of geostationary imagery over the Indian Ocean and Pacific Ocean EUM/STG/75/19/DOC/12 CORR1
CGMSSEC | WGIII/7 | WGIII/A47.09 | CGMSSEC to write to NSOAS stating the importance of HY-2B MWI and ALT data. | 2019 Nov 22: CGMS/LET/19/1138229 sent to NSOAS (informing WGIII Co-chairs and rapporteur by e-mail) | Dec 2019 | CLOSED
NOAA | WGIII/7 | WGIII/A47.10 | MW imaging in LEO for SST: NOAA to provide an update on SSMI status and possible follow-on | 2020 Feb 19: This action is broader and well beyond the SSMI. NOAA is in discussion with DOD on the follow on of the DMSP. A related action from plenary is likely to be transferred from Take action from plenary and transfer to WGIII (same action) | CGMS-48 | OPEN
ISRO | WGIII/7 | WGIII/A47.11 | ISRO to provide an update on its plans for follow-on mission to Oceansat-3A. | 2020 Feb/April: - | CGMS-48 | OPEN
ISRO | WGIII/7 | WGIII/A47.12 | ISRO to confirm data latency for Aditya-L1 mission | 2020 Feb/April: - | CGMS-48 | OPEN
ISRO | WGIII | WGIII/A47.13 | On passive microwave observations: ISRO is recommended to confirm its plans for a Megha-Tropiques follow up mission in low inclination and its plans for TSU and MSU MW sounders and to consider complementary orbits for the deployment of these sounders. (Formerly plenary recommendation R46.07) | 2020 Feb/April: - (CGMS-47: transferred from plenary recommendation to WGIII action) | CGMS-48 | OPEN
JAXA, NASA | WGIII/7 | WGIII/A47.14 | NASA and JAXA to provide future plans for precipitation measurement mission(s) | 2020 Feb/Apr: - 2020 29 Jan, IS #1: NASA and JAXA have extended their GPM agreement until 2029 (EUMETSAT's associated agreement is currently being extended accordingly). The JAXA next gen AMSR3 has been approved to fly on | CGMS-48 | OPEN
WGIII | WGIII/7 | WGIII/A47.15 | WGIII to update the CGMS Baseline and conduct the annual Risk Assessment for submission to CGMS-48 | 2nd CGMS WGIII risk assessment workshop held at EUMETSAT on 2020 Feb 19-21. Outcome/report to be discussed in WGIII at CGMS-48 for endorsement by plenary (CGMS-48 CGMS-WP-10 and -12). 2020 29 Jan, IS #1: To be reviewed at the 2nd risk assessment WS 19-21 Feb 2020. | CGMS-48 | ONGOING
EUM | WGIII/ | WGIII/A47.16 (WGIII R46.01) | CGMSSEC to enquire with EUMETSAT NWP SAF Radiative Transfer Model (RTM) support for FY-2E/H Indian Ocean coverage. (Formerly WGIII recommendation R46.01) | 2020 Feb 19: RTTOV is supporting FY-2 VISSR sensors as can be seen in this web page: https://www.nwpsaf.eu/site/software/rttov/documentation/platforms-supported/ (Changed from recommendation to action. CGMS-47 WGIII discussion: Recommendation to be passed to EUMETSAT) | Dec 2019 | CLOSED?
WGIII | from WGII/5 | WGIII/A47.17 (WGII/A47.14) | WGIII to provide their assessment and planning for the next risk assessment to the ISWGs, WGClimate and GSICS. (Action from WGII). | 2020 Feb 19: 2nd risk assessment workshop held on 19-21 Feb 2020.Will be addressed at inter-sessional meetings and at CGMS-48 | Apr/Mar 2020 | OPEN
CGMS-47 WGIII Recommendations
Lead | AGN item | Rec # | Description | Recommendation feedback/completion document | HLPP ref
CGMS space agencies | From plenary 5.7 | R47.01 | (From IPWG): IPWG strongly recommends to CGMS members to continue the constellation of PMW sensors to ensure quality satellite precipitation products for weather, climate, and hydrological applications. Additionally, IPWG would like to be kept informed of longer term plans for subsequent launches of microwave sensors to ensure continuity of long-term observations that meet the documented needs of the user community. | Transferred from plenary
CGMS space agencies | From plenary 5.7 | R47.02 | (From IPWG): IPWG also recommends that there be a CGMS-wide coordination of the crossing times of precipitation relevant satellites in an effort to improve the temporal sampling of diurnal cycle, convective systems lifecycles, and severe storms. | Transferred from plenary
CGMS space agencies | From plenary 5.7 | R47.03 | (From IPWG): As precipitation moves to higher temporal rates, we recommend to CGMS members to synchronize full-disk geostationary sampling schedules which will optimize GEO scans to improve temporal sampling of precipitation products and unknown future PMW imager availability for merged products. | Transferred from plenary
CGMS space agencies | From plenary 5.7 | R47.04 | (From IPWG): Collaboration between space programs and data assimilation centers should be specifically encouraged to incorporate DA requirements as part of scientific requirements when developing new satellite / observing systems. This would reduce barriers for operational assimilation of observations, and potentially provide a greater range of utility for various sensors. | Transferred from plenary
CGMS space agencies | From plenary 5.7 | R47.05 | (From IPWG): Higher spatial and temporal (sub-hourly) resolution and higher spectral sampling in the microwave measurement of clouds and precipitation should be considered in future observing systems. | Transferred from plenary
CGMS space agencies | From plenary 5.7 | R47.06 | (From IPWG): Latency and quality of satellite data should be improved, from both operational and research missions, to fit in the DA high temporal resolution cycle. | Transferred from plenary
1st risk assessment workshop Feb 2019 - recommended mitigations actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status
WMO |  | 1RAWS2019.1 | WGIII recognised the need for continuity in the Early Morning Orbit and the gap it creates on microwave sounding, infrared sounding, multi-purpose imaging, visible/IR radiometer, ion/electron/proton spectrometer, and scatterometer observations. Recommended Mitigating Action #1: WMO to reconvene a WMO-CGMS Tiger Team on the impact of the Early Morning orbit. | Feb 2020, 2nd CGMS risk assessment workshop: This action is included in and monitored through the CGMS WGIII list of actions- leave status neutral? | CGMS-48 | OPEN
WMO, IROWG |  | 1RAWS2019.2 | WG III recognised that Radio Occultation does not meet the CGMS Baseline after 2025. Recommended Mitigating Action #2: IROWG and 7th WMO Impact Workshop needs to validate the current Baseline in terms of the coverage, number, quality and sampling of RO. | Feb 2020, 2nd CGMS risk assessment workshop: Pending outcome of next IROWG meeting, and WMO impact workshop in May 2020. | May 2020 | OPEN
IODC sat obs space agencies |  | 1RAWS2019.3 | WG III recognised the gap in overall resilience and coverage of GEO in the IODC region. Recommended Mitigating Action #3: Conduct a study on the GEO imager coverage, data quality, availability and resilience in IODC region. | Feb 2020, 2nd CGMS risk assessment workshop: EUMETSAT presented an overview indicating there is a reasonable resilient provision of data currently in the region. This will be presented and addressed at CGMS-48. | CGMS-48 | ONGOING
EUM and NSOAS |  | 1RAWS2019.4 | WGIII recognised the need for a long term plan for ~6Ghz frequency microwave imaging in at least one LEO orbit for all weather Sea Surface Temperature observations. Recommended Mitigating Action #4: [EUM and SOA] to ensure data availability for HY-2B MWI. | Feb 2020, 2nd CGMS risk assessment workshop: NSOAS has confirmed they will attend CGMS-48. To be addressed on this occasion. | CGMS-48 | OPEN
CGMS space agencies |  | 1RAWS2019.5 | Recommended Mitigating Action #5: CGMS Members to continue to support High Level Priority Plan 1.2.2. | Feb 2020, 2nd CGMS risk assessment workshop: … | CGMS-48 | OPEN
NOAA |  | 1RAWS2019.6 | Recommended Mitigating Action #6: NOAA to provide an update on SSMI status and possible follow-on. | Feb 2020, 2nd CGMS risk assessment workshop: To be addressed at CGMS-48 at the latest? | CGMS-48 | OPEN
GSICS / GSICS EP |  | 1RAWS2019.7 | WGIII recognised that there is adequate coverage of microwave imaging, but operational usefulness is limited because the imagers are not cross calibrated. Recommended Mitigating Action #7: GSICS to continue cross calibration progress of microwave imagers. | Feb 2020, 2nd CGMS risk assessment workshop: To be addressed at the upcoming GSICS meeting in March 2020 and at the GSICS EP meeting in May 2020. | Mar and May 2020 | OPEN
EUM and NSOAS |  | 1RAWS2019.8 | WG III recognised that there is no radar altimetry data availability in the early morning orbit in the short term and that there are no plans in the long term for coverage. Recommended Mitigating Action #8: [EUM and SOA] to ensure data availability for HY-2B ALT. | Feb 2020, 2nd CGMS risk assessment workshop: NSOAS has confirmed they will attend CGMS-48. To be addressed on this occasion. | CGMS-48 | OPEN
ISRO |  | 1RAWS2019.9 | WG III recognised scatterometer observations are at risk of a gap in the early morning and afternoon orbits after 2025. Recommended Mitigating Action #9: ISRO to consider follow-on mission to Oceansat-3A. | Feb 2020, 2nd CGMS risk assessment workshop: Pending feedback from ISRO. | CGMS-48 | OPEN
ISRO |  | 1RAWS2019.10 | Recommended Mitigating Action #10: ISRO to consider making scatterometry data available to all CGMS Members. | Feb 2020, 2nd CGMS risk assessment workshop: Pending feedback from ISRO. | CGMS-48 | OPEN
2nd risk assessment workshop Feb 2020 - recommended mitigations actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status
|  | 2RAWS2020.1 |  |  |  | OPEN
|  | 2RAWS2020.2 |  |  |  | OPEN
|  | 2RAWS2020.3 |  |  |  | OPEN
|  | 2RAWS2020.4 |  |  |  | OPEN
|  | 2RAWS2020.5 |  |  |  | OPEN
|  | 2RAWS2020.6 |  |  |  | OPEN
|  | 2RAWS2020.7 |  |  |  | OPEN
|  | 2RAWS2020.8 |  |  |  | OPEN
|  | 2RAWS2020.9 |  |  |  | OPEN
|  | 2RAWS2020.10 |  |  |  | OPEN

## CGMS-47 WGIV
WGIV actions open from previous plenary sessions (at CGMS-47)
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
EUM | WGIII/2 | A43.02 | (Action transferred from WGIII) EUMETSAT to propose dissemination plan for data from Indian Ocean Data Coverage partners identified in CGMS-43-EUM-14 roadmap. | 2019, 10 Dec, IS WGIV: Pending: CMA-EUM bilateral Feb 2020 Elektro-L2 product availability 2019 Nov: Further feedback expected by Feb 2020. CGMS-47: Availability of Elektro-L N2 meteorological products to be discussed with Roshydromet. CMA to provide status of implementation of IODC products on CMACast. Implementation of all other products on EUMETCast Africa and provision to CMA completed. 5 Dec 2018: Elektro-L N2 meteorological products not yet available. Implementation of all other data at EUMETSAT side (EUMETCast Africa) completed. Access for CMA via EUMETCast Terrestrial in progress, to be completed latest Jan 2019. CGMS-46: Progress reported in CGMS-46-EUMETSAT-WP-08 CGMS-46-ISRO-WP-05 and closure expected in autumn 2018. WGIV IS-1, Oct 2017: EUMETSAT: work in progress, pending dissemination facility upgrade and EUMETCast Africa contract renewal in 2018, and pending decision to add more data Status at CGMS-45: CGMS-45-EUMETSAT-WP-37 CGMS-45-ISRO-WP-05 Ongoing work, deadline extended. WGIV webex 9 Dec 2015: WMO seeking to assure that the dissemination to users will be equivalent to the current one (EUMETSAT, CMA, ROSH and ISRO to collaborate and clarify this in view of CGMS-44. EUMETSAT makes FY-2E data available through EUMETCast. EUM expects its Council to take a decision on moving Meteosat-8 to ca 40° E in June 2016. CGMS-44 EUM-WP-14 WG-IV webex/communication 18 Jan 2017: Status of IODC Service by CMA: The CMA FY-2E at 86.5E is undertaking IODC service. CMA shall keep continuity of IODC service at 86.5E, on assumption: - FY-2G, launched 31 December 2014, currently operating at 105E; - Launch of FY-2H is planned for the end of 2017 or early 2018. | Feb 2020 (Dec 2019) (CGMS-44/45/46) | OPEN | 1.1
CGMSSEC, WMO, space agencies | WGIV (WGII) | A44.05 | From CGMS-44 WGII: CGMS operators and WMO to work with GODEX-NWP to explore options for optimal data exchange of advanced data from next-gen GEOs. | 2019, 10 Dec, IS WGIV: Included in the WGIV agenda for CGMS-48. 2019 Nov: Currently no specific requirements from GODEX-NWP. To be discussed in future WGIV intersessionals. CGMS-47: Current situation is ok, no specific requirements. Satellite operators will certainly address regional requirements for their next-gen satellites. Future global (next-gen satellite) requirements will be addressed in an inter-sessional meeting with GODEX-NWP participation . and CC Matt Buttler and Simon Eilliott 12 Nov 2018: Pending outcome of the GODEX-NWP meeting. At CGMS-46: No further input, feedback from GODEX-NWP required. 22 May 2018: To be discussed in WGIV at CGMS-46, which needs participation/representation from WGII to explain the background and purpose to enable WGIV to move forward. The next GODEX-NWP meeting will be held 27-30 Nov 2018 in New Delhi, India. WG-IV WEBEX 18 Jan 2017: WMO: GODEX-NWP scheduled May 2017, needs will be addressed there, WMO will provide feedback. CGMS-45: GODEX-NWP not yet ready to provide feedback. | CGMS-48 (CGMS-45/46/47) | OPEN | 3.12
TFMI | WGIV/9 | A45.02 | TFMI to work on the WIGOS metadata standard, in particular to assess the WIGOS Metadata OGC Observations and Measurements standard, and recommend possible adjustments for satellite observations to the WMO WIGOS team. | 2019, 10 Dec, IS WGIV: TFMI report to be made to CGMS-48 CGMS-47: included in work plan of TFMI Oct 2018: A WIGOS metadata assessment provision to IPET WIGOS by March 2019 is feasible. The work is divided in two steps. In the first step an assessment to be done of the abstract (the standard), and an assessment from satellite providers. (March 2019) The second step is the assimilation in XML, i.e. the transport level. (July 2019) CGMS-46: No progress due to lack of resources by TFMI key members, will be addressed with TFMI in inter-sessional meetings. | CGMS-48 (CGMS-46) | OPEN | 3.9.1
TFMI | WGIV/12.1 | A45.03 | CGMS satellite operators to provide documentation on the data formats for space weather observations, and to forward related space weather metadata to the WIS. | 2020, 5 Feb: Use of GRIB-2 format had been approved (WMO). T Onsager stated that this format is not the best way forward for transfer of SpWx information and that the NETCDF format would be a better choice. Please refer to the email exchange “GRIB-2 data format for Space Weather data” following the meeting. The formats required by the SpWx community (currently and for the future) need to be compiled and this can be addressed by SWCG together with CGMS WG-IV (taking account of the survey results) 2020 Jan 21 SWCG IS #3: Werner Balogh pointed out the SPASE model (http://www.spase-group.org/about.html) is being used within the International Space Weather Initiative (ISWI) data policy. Toshi Kurino recalled that the GRIB2 data format usage for space weather remains to be clarified. Note that on this subject, the CGMS-47 SWCG report states: “The request from WMO-CM to SWCG concerning the usage of the GRIB Edition 2 format was discussed. SWCG requested WMO to recommend that IPT-SWeISS give their feedback in the first instance.” - Elsayed and Nagatsuma-san will follow up on this with IPT-SWeISS 2019, 10 Dec, IS WGIV: TFMI report to be made to CGMS-48 CGMS-47: Space weather metadata aspect to be assessed by TFMI. Remaining action superseded by ongoing Space Weather data provider survey (SWCG/A47.05) Nov 2018: A survey is ongoing by TFMI to be concluded by end 2018 for the establishement of a best practice. 2018 Oct 8, SWCG IS#2 webex: WMO pointed out the SPASE model (http://www.spase-group.org/about.html) is used within the International Space Weather Initiative (ISWI) data policy. CGMS-46-NICT-WP-02 see also CGMS-46 WGIV/12.1 | CGMS-48 (CGMS-46) | OPEN | 3.10
WG IV | WGII/4 | A45.05 | Action from WGII: Ensure timely (< 1 hr) and free access to all geostationary visible, IR and water vapour data that is required to improve global hydrological prediction. | 2019, 10 Dec, IS WGIV: Pending information from WMO At CGMS-47: Pending response from WGIV/A46.02 Put on hold until requirements are clarified (see new action A46.02) 29 May 2018: NOAA provides this data at the requested latency. 14 Mar 2018: IPWG recognises it is not feasible having all channel data from the new era of GEO satellites, however: a) At a minimum, sustained 30-min refresh full disk longwave IR (10 to 15-min desired), near realtime access; b) Given the expanded spectral bands of the operational global geo constellation, additional 6.2 um water vapor channel data, at the same refresh as IR c) Finally, visible channel data desired 25 Oct '17: CGMSSEC has sent a message to IPWG co-chairs to this purpose asking for more details to enable WGIV to react. [enquiry sent to R Ferraro 19 Feb 2018] WGIV IS 11 Oct '17: This action was discussed and WGIV concluded the request is too open and would have a significant impact on the data access in this form. The following clarification was formulated and CGMSSEC is asked to pass this on to the IPWG: The precipitation community to clarify what data are needed, in terms of time/spatial resolution, spectral channel selection, and sub-setting. CGMSSEC to follow this up with IPWG. | CGMS-48 | OPEN
WMO | WGIV/3.2 | A46.02 | WMO to further refine the requirement from IPWG for GEO image data, in terms of users and geographical resolution | 2020 Jan 24 from WMO: A stated requirement for global GEO imagery to support precipitation monitoring to be provided by SCOPE-NowCasting Pilot Project 3 (point of contact Daniel Vila daniel.vila@inpe.br) at IPWG-10 in June 2020. The IPWG meeting should also consider any needs to further refine the global requirements in terms of identified users and geographical resolution. 2019, 10 Dec, IS WGIV: Pending information from WMO 2019 Nov 18: CGMSSEC contacted WMO & IPWG by e-mail. | Dec 2019 (CGMS-47) | OPEN
WMO | WGIV/6 | A46.03 | WMO to liaise with GSICS on implementing GSICS monitoring capabilities in WDQMS, to include incident management capabilities, and report back to WG-IV, proposing a way forward | 2019, 10 Dec, IS WGIV: Pending information from WMO Side Meeting between GSICS and WMO regarding WDQMS. WMO will invite GSICS to attend next TT-WDQMS meeting. | CGMS-48 | OPEN
CGMS satellite operators | WGIV/7 | A46.04 | To consider an enhancement of advance notifications of processing changes as specified below and provide feedback to WG-IV. If a planned change to data processing results in a change in brightness temperature of 0.1K or 20% of NEdT (whichever is smaller), this should be made clear in notifications to users. These notifications should be made no later than 8 weeks before the change and test data should be provided if possible. [From the ITWG ITSC-21 Report] | 2019, 10 Dec, IS WGIV: Clarified that this action is about developping specific thresholds for notifications, not about the notification system itself. CGMS-47: EUMETSAT: A general change and user notification process is in place. An analysis is in progress w.r.t. the requested specification. Results to be discussed in an inter-sessional meeting. 5 Dec 2018: It was clarified that "instrument changes" means changes w.r.t. performance, and not changes vs specification. Nov 2018: EUMETSAT has an implemented process. | Dec 2019 (CGMS-47) | OPEN
CMA | WGIV/7 | A46.05 | To consider implementing a subscription-based anomaly/event notification service, similar to that provided by NOAA and EUMETSAT and provide feedback to WG-IV. | CGMS-47: System is under construction. | Dec 2019 (CGMS-47) | OPEN
WGIV | (Plenary E.10) | A46.06 | Following CGMS-46 plenary discussions related to IROWG and GCOS IP: CGMS WGIV to consider the GCOS IP actions on long-term data preservation (LTDP). Ref. GCOS IP action G 26. | 2019, 10 Dec, IS WGIV: CEOS BP doc exists. The adopting the CEOS LT preservation guidelines under finalisation. ISRO/Nitant Dube to share the URL once ready. 2019 Nov 20: EUM and NOAA input provided. Get response from other agencies if possible, then prepare Best Practise on this basis. CGMS-47: NOAA: Under federal law, supported by a suite of policies and procedures (see below for a summary), NOAA ensures through its National Environmental Satellite, Data, and Information Service (NESDIS) and the National Centers for Environmental Information (NCEI) that level 0 and level 1 satellite data, along with metadata and derived level 2 and higher products, are preserved for the long term and made available to the public at no more than the cost of reproduction. EUM Nov 2018: EUMETSAT fully recognises the importance of early satellite data for climate activities and follows the CEOS Preservation Guidelines, documented in "Long Term Preservation of Earth Observation Space Data". In adopting these guidelines and the relevant operational processes EUMETSAT ensures the long-term preservation and usability of (early) satellite raw and level 1 data, including metadata. For all EUMETSAT missions, the raw data and metadata as well as the derived level 1 and level 2 products are archived and preserved in the EUMETSAT Data Centre. The level 1 and level 2 data are accessible online and free of charge by users. The generation of high quality FCDRs and TCDRs from the preserved raw extending back to the first availability of data is an important part of EUMETSATs climate activities, e.g. Meteosat First Generation (MVIRI) FCDR covering the time period from 1981-2017). (Addressed in the latest version of the HLPP) | Dec 2019 | OPEN
CGMS satellite operators | IS-2 | A46.08 | CGMS members to review the "CGMS/WMO best practices for achieving user readiness for new meteorological satellites" (https://www.cgms-info.org/documents/CGMS-BP_user_readiness_Apr2016.pdf) and to provide feedback and make recommendations on updates. | 2019, 10 Dec, IS WGIV: To be discussed in dedicated WGIV IS before CGMS-48 2019 Nov 20: To be reviewed and addressed at a dedicated intersessional meeting for follow-up in a dedicated sub-group. CGMS-47: action refined | CGMS-48 | OPEN | 3.2.1
CGMS-47 WGIV actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
CGMS members | WGIV/8 | A47.01 | Big data/cloud services: To provide a point of contact for participation in regular inter-sessional teleconferences lead by NOAA, starting discussions to establish an expert group on cloud services interoperability. | Agencies to provide PoCs. NOAA: (vanessa.l.griffin@noaa.gov) EUM: lothar.wolf@eumetsat.int ISRO: Nitant Dube nitant@sac.isro.gov.in JMA: K Bessho kbessho@met.kishou.go.jp | July 2019 | OPEN | 3.7
CGMS members | WGIV/8 | A47.02 | To analyse if existing cloud service activities can serve as a demonstration project, exploring at least two of the WMO Information Systems (WIS 2.0) principles. | Agencies to provide PoCs. EUM: lothar.wolf@eumetsat.int | CGMS-48 | OPEN
CMA, JMA,KMA, WMO | WGIV/9 | A47.03 | To liaise with WMO and prepare the report of RSS observation activities including user readiness and notification. | JMA-CMA-KMA discussion held at recent AOMSUC and will report progress to next CGMS. | CGMS-48 | OPEN | N/A
NOAA | WGIV/12 | A47.04 | To support enabling the connectivity between the OAI PMH NESDIS repository and GISC Washington, to be able to harvest metadata. | 2019, 10 Dec, IS WGIV: M Butler to follow up. | July 2019 | OPEN | 3.8
CGMS members | WGIV/15 | A47.05 | To provide a point of contact for participation in regular inter-sessional teleconferences on cyber security including related training aspects. | Agencies to provide pocs. NOAA: (vanessa.l.griffin@noaa.gov) EUM: guillaume.texier@eumetsat.int ISRO: Nitant Dube to confirm JMA: K Bessho kbessho@met.kishou.go.jp | July 2019 | OPEN | N/A
CGMS-47 WGIV Recommendations
Lead | AGN item | Rec # | Description | Recommendation feedback/closing document | HLPP ref
CGMS | WGIV/12 | R47.01 | CGMS-47 Plenary to endorse the recommendations available from CGMS-TFMI-WIGOS-Standard-Review (link see CGMS-47-CGMS-WP-07). | CONCLUDED Endorsed by CGMS-47 plenary. | 3.9.1
CGMS | WGIV/12 | R47.02 | CGMS-47 Plenary to endorse the presented working plan regarding the assessment of the WIGOS Metadata Representation Format and allow the task force to proceed on the defined tasks. | CONCLUDED Endorsed by CGMS-47 plenary. | 3.9.1
CGMS | WGIV/13 | R47.03 | CGMS-47 Plenary to endorse the Five‐year Strategy document proposed by VLab, w.r.t. items in the scope of WG-IV. | CONCLUDED CGMS-47 plenary endorsed the Vlab 5-year strategy. | 5.2.1
CGMS members | WGIV/3.2 | R44.02 | CGMS members to continue the provision of up-to-date User Readiness information in the SATURN portal | 2019, 10 Dec, IS WGIV: at CGMS-47: consider conversion into best practise during inter-sessional meeting | 3.2.2
CGMS space agencies | WGIV/7 | R42.01 | Satellite operators to provide WIS Discovery Metadata Records, compliant to WIS requirements and following the guidance to be provided by the CGMS-WMO Task Force on metadata implementation, in order to facilitate satellite information discovery and access | 2019, 10 Dec, IS WGIV: at CGMS-47: consider conversion into best practise during inter-sessional meeting | 3.7
CGMS space agencies | WGII/10 | R43.07 | CGMS agencies to make available a non real-time cache of satellite level 1 data over the previous 2-3 months, similar to the NOAA CLASS system. | 2019, 10 Dec, IS WGIV: at CGMS-47: consider conversion into best practise during inter-sessional meeting
Actions to be reviewed in the medium term:
CGMS members | WGIV/16 | A47.06 | CGMS members, through WGIV, to review CGMS members’ adherence levels to the CEOS Data Preservation Guidelines on a regular basis (every 2-5 years). For review at CGMS in the 2023-2024 timeframe. | 2019, 10 Dec, IS WGIV: CGMSSEC/Anne to raise it with MRa if this should be covered by the HLPP. ISRO/Nitant Dube will secure that CGMS is informed once new version(s) of the CEOS DP guidelines are available. (The related recommendation was endorsed by CGMS-47 plenary). | 2023-2024 | OPEN

## CGMS-47 SWCG
CGMS-47 SWCG actions
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
SWCG | SWCG/3 | A47.01 | CCMS members to assess whether magnetorquer TM can be extracted to allow assessment for magnetic field derivation | 2020 April 1, IS#4: to confirm closure of AI 47.01 (extraction of magnetorquer telemetry does not provide sufficient benefit for the expected effort). Currently not seen as providing sufficient value on the necessary investment. Propose to close at IS#4 unless further interest expressed. 2020 Jan 21 SWCG IS #3: Initial EUMETSAT investigation made for Metop satellites; telemetry is available for the satellite wheels and magnetorquers which could make it possible to derive an optimised magnetic field to match the torque equilibrium. However that would require quite significant effort and the result would be quite dependent on how accurately we can model the external torques (gravity, solar radiation, drag, satellite magnetic dipole). This could be suggested as a project for a university student, but not an activity EUMETSAT would envisage performing with existing resources. 2019 Nov 5: ESA (J-P Luntama): “Regarding the action SWCG/3, I have promised to provide results from a recent ESA study on this topic (see e.g. https://www.esa.int/Enabling_Support/Space_Engineering_Technology/Satellite_compasses_open_new_window_on_space_weather for some additional info). However, the final report from the study is not available yet and I am not completely sure when it would become available. I will see the study TO tomorrow and I will ask him again about the report. So, the answer to the action is very certainly "yes", but availability of the data is mission specific and not all space missions are designed to easy access for TM data. It is also still uncertain if this data can be used in near real-time as filtering out spacecraft interference requires a substantial amount of processing. The SOSMAG concept that we have now successfully demonstrated with GK2A may still be an easier way to fly dedicated magnetometers on magnetically noisy environments.” No other inputs from SWCG members have been made yet (Action remains OPEN). Part-1 conclusion: Currently not seen as providing sufficient value on the necessary investment 2018 Oct 8, SWCG IS#2 webex: An ESA study has been performed. ESA to send report when available. It was noted there could be some issues extracting the embedded TM data. | Apr 2020 (Jul 2019) | PRO-POSED CLOSURE? | 1.1.2
SWCG | SWCG/3 (WGIII) | A47.02 | Survey ISES on need for operational spaceborne LEO magnetometer data and propose updates to CGMS Baseline as appropriate. | 2020 april 1, IS#4: 2020 Jan 21 SWCG IS #3/2020 Feb 5: Action on ESA/NASA/Russia – Provide the plans for future magnetometer missions in LEO (scientific or operational objectives). LEO magnetometer data is not integrated into operational SpWx services – more research / modelling analysis required. Action on ISES - Survey the ISES members further to assess their need for the magnetometer data and timeline for these needs. Can then decide on whether to remove the magnetometer in LEO from Baseline and identify it instead as an aspirational mission type. Risk Assessment Workshop (WGIII) – Taking place at EUMETSAT from 19-21 February. Andrew Monham will represent SWCG related issues there. Included in the user survey (Ref. SWCG/ A47.06). Survey is completed, some data users realize the importance of magnetometer data for model comparison, and producing the global distribution of high energy particle – should we include magnetometer data in the baseline? Part-1 conclusion: Action on ESA/NASA/Russia – Provide the plans for future magnetometer missions in LEO (scientific or operational objectives). Action on ISES - Survey the ISES members further to assess their need for the magnetometer data and timeline for these needs. Can then decide on whether to remove the magnetometer in LEO from Baseline and identify it instead as an aspirational mission type. 2018 Oct 8, SWCG IS#2 webex: Included in the ongoing survey (issued on 26 Sep 2019). | Apr 2020 (Jul 2019) | OPEN | 1.1.2
SWCG | SWCG/3 | A47.03 | Encourage WMO CGMS Early Morning Tiger Team to include Space Weather data in their impact analysis. | 2018 Oct 8, SWCG IS#2 webex: It is noted that this request has already been made in the WGIII action list (WGIII/A47.01) . E Talaat is a member of WGIII and will help ensure this is followed up. However, discussions are not foreseen to take place in the near future. The SWCG action can be closed, as it is pursued through the WGIII action. (CGMS-47: The study is expected to be carried out in 2020/2021 timeframe, launch ~2021) | CGMS-48/-49 | CLOSED | 1.1.2 | ESA 5 Nov 2019: Results from a recent ESA study on this topic (see e.g. https://www.esa.int/Enabling_Support/Space_Engineering_Technology/Satellite_compasses_open_new_window_on_space_weather for some additional info). However, the final report from the study is not available yet. Answer is very certainly "yes", but availability of the data is mission specific and not all space missions are designed to easy access for TM data. It is also still uncertain if this data can be used in near real-time as filtering out spacecraft interference requires a substantial amount of processing. The SOSMAG concept that we have now successfully demonstrated with GK2A may still be an easier way to fly dedicated magnetometers on magnetically noisy environments.
SWCG | SWCG/7 | A47.04 | Propose improvements to the space weather parameters in the OSCAR DB and request support for implementation from WMO. The parameters available in the existing DB may not be sufficient to properly describe measurement capabilities of SW instrumentation. | 2020 april 1, IS#4: 2020, 5 Feb: OSCAR database was updated by NOAA in Fall 2019 – NOAA/NASA “OSCAR NOAA-NASA SpWx update2019. WMO have sent a table to SWCG for feedback on the various SpWx missions: ”Space Weather-OSCAR-template-11Nov2019”. Background information is contained in the IPT-SWEISS doc: Space-weather-in-OSCAR-10Nov2019. ACTION on all SWCG Members to fill this out Debate concerning the separation of scientific and operational usage – not viewed as a feasible categorisation by WMO. Better to record the actual data latency as provided by the satellite operator/data provider. Same with reliability. See if can use a searchable field rather than free text. 2020 Jan 21 SWCG IS #3: - The WMO 4 year plan 2020-2023 was approved by Congress (Cg-18 Res. 53). A presentation on this and overall WMO space weather activities was kindly provided post-meeting by Werner Balogh and is attached to IS#1 Minutes. WMO require this action input to OSCAR as soon as possible. The IPT-SWeISS meeting in November will be the next opportunity to discuss progress. - It is possible that changes to the DB structure and code may be required, not just variables / parameters. - Elsayed (NOAA) and Nagatsuma-san (NCIT) will provide recommendations as soon as possible. Note that the review need not be limited to your own organisation’s assets. - Action remains OPEN. (NOAA/NASA provided a presentation at the IS #3 mtg) Part-1 conclusion: Debate concerning the separation of scientific and operational usage – not viewed as a feasible categorisation by WMO. Better to record the actual data latency as provided by the satellite operator/data provider. Same with reliability. See if can use a searchable field rather than free text. WMO have sent a table to SWCG for feedback on the various SpWx missions – this needs to be filled in by NASA/NOAA/ESA in particular. 2018 Oct 8, SWCG IS#2 webex: - The WMO 4 year plan 2020-2023 was approved by Congress (Cg-18 Res. 53). WMO provided a presentation on this and overall WMO space weather activities to SWCG in Oct 2019. WMO requires this action input to OSCAR as soon as possible. The IPT-SWeISS meeting in Nov 2019 will be the next opportunity to discuss progress. - It is possible that changes to the DB structure and code may be required, not just variables / parameters. - SWCG co-chairs to provide recommendations asap. | CGMS-48 | OPEN | 3.10
SWCG | SWCG/8 | A47.05 | CGMS Members to complete the on-going Space Weather data provider survey | 2020 april 1, IS#4: 2020 Jan 21 SWCG IS #3: Data providers survey inputs received from NOAA, NICT and ESA.CGMS members invited to provide remaining responses. Proposed to close action based on results received at CGMS-48. 2018 Oct 8, SWCG IS#2 webex: - Roshydromet, CMA and KMA are kindly requested to provide a response to the Data Providers Survey issued on 1 March 2019 as soon as possible, as these organisations are important providers of space weather data from their satellites (refer to the NOAA input to help with understanding of the level of information required. - The GNSS RO WG has a subgroup dealing with Space Weather and should be requested to provide inputs to the data provider survey. Examples are NASA Cosmic-2. For KOMPSAT, it is not clear weather ionosphere data is provided for SpWx usage. The Spanish PAZ satellite also operates a RO mission, although it is also unclear whether any ionospheric data is acquired. Elsayed to contact the GNSS RO WG / NASA /KMA with the survey and request this information. - It is noted that commercial RO data evaluations are ongoing, including ionospheric measurements (NOAA /EUMETSAT activity). | May 2019 | OPEN | 3.11
SWCG | SWCG/8 | A47.06 | Identify Space Weather Data and Services Users and send survey including findings from the Data Providers Survey for their comment. | 2020 april 1, IS#4: 2020, 5 Feb: Summary of the inputs received was made using the ESWW presentation “TDM CGMS presentation…”. Further attempts to get survey inputs will be made by Werner Balogh / Jussi, when attending the UN Expert Committee in Vienna, 4-6 February. Also to be followed-up with ISES to encourage more inputs (Jesse Andries) and at the US SpWx Workshop 20-24 April. Discussion on the actions / focus of the various SpWx groupings: CGMS/SWCG, ISES, IPT-SWeISS, ISWI, etc.– need to ensure that we remain coordinated. Action on Andrew Monham and Terry Onsager to review user survey responses received and clarify open points with respondents on an individual basis (before CGMS-48). 2020 Jan 21 SWCG IS #3: Data User Survey – 11 inputs from BDV (Czech), BOM (Australia), China (NAOC), DLR (Germany), NICT (Japan), NOAA SWPC, Qinetic (UK), SES (Luxemburg), SWIFtS_LAPAN (Indonesia), Met Office MOSWOC (UK), UKRI STFC RAL Space (UK). Various levels of completeness. See attached presentation with summary presented at ESWW. - Will need to contact these institutions individually. - Clearly some issues getting access to reliable / timely in-situ data. 2018 Oct 8, SWCG IS#2 webex: - Survey of Space weather service providers (as the primary users of space weather instrument data provided by the CGMS Members) issued on 26 Sep 2019 for completion by 21 Oct 2019. WMO/Balogh has forwarded this further to ISWI. Target is to discuss all survey results data providers and users (service providers) in the meeting scheduled for the ESWW in November 2019. Review meeting of results scheduled for 4 November (Elsayed, Nagatsuma-san, Jussi, Ken and Andrew). | June 2019 | OPEN | 3.11
SWCG | SWCG/8 | A47.07 | Establish a small task group to identify gaps and disconnects from service and perspective of operational space weather communities (e.g. ICAO, ISES, etc.) with objective to report out in Jan 2019 | 2020 april 1, IS#4: 2020 Jan 21 SWCG IS #3: Pending the outcome of SWCG A47.05 and SWCG A47.06 2018 Oct 8, SWCG IS#2 webex: Pending outcome of actions SWCG A47.05 and SWCG A47.06. | July 2019 | OPEN | 6.2.1
SWCG IC TG | SWCG/9 | A47.08 | Space Weather Inter-calibration Task Group members to agree on a specific period of data for validating the inter-calibration approach for high energy particle sensors on-board GEO satellites. | 2020 april 1, IS#4: 2020, 18 Feb: SW IC Task group inter-sessional - outcome? 2020 Jan 21 SWCG IS #3: Nagatsuma-san email of 29 November following satellite data was provided to this task group. - Himawari 8 - FY satellites - Integral IREM Terry Onsager provided info on GOES-16 data on 8 January. 2018 Oct 8, SWCG IS#2 webex: There will be an IC TG teleconference om the period 10-17 Oct 2019 at 12 UTC. CMA and KMA participation is requested. Action due date postponed to November 2019. | Nov 2019 (Jul 2019) | OPEN | 6.2.2 4.1
SWCG IC TG | SWCG/9 | A47.09 | Space Weather Inter-calibration Task Group to produce a "White Paper" with the objective of getting feedback from GSICS on issues faced by CGMS members concerning inter-calibration of high-energy particle sensors, including, how to share data, use of each sensor for space weather products, identified problems and associated estimates of effort. Consider also the inter-calibration issues of other space-based space weather observation. | 2020 april 1, IS#4: 2020 Jan 21 SWCG IS #3: Open (TBC if sufficient progress on the SpWx inter-calibration activity will be made in ime for the GSICS mid-March 2020 meeting). 2018 Oct 8, SWCG IS#2 webex: Due date Feb 2020 to provide input in time for GSICS meeting in March 2020. | Feb 2020 (Jul 2019) | OPEN | 6.2.2 4.1