## Sheet1
WGIII list of actions following CGMS-53
Actionee | AGN item | Action # | Description | Action feedback/closing document | Deadline | Status | HLPP ref
WGIII & WGII | 7.1 | WGIII/52.03 | WGIII to recommend to WGII the need for articulating MW missions with different frequencies in the CGMS baseline and risk assessment in the future and how to visualise it in the flyout charts | 8RAWS: Proposal made, to be reviewed at the WGIII IS in March and confirmed at WGIII session in April. Close to completion will be addressed at the 8th risk assessment WS. A proposal has been made which is expected to be implemented for the 9th risk assessment review (2027). WGIII IS#2, WMO and the IPWG have prepared a document that will be shared with WGII (@Heikki Pohjola) for their consideration. Work ongoing to propose MW frequencies in the documents. Meeting with IPWG (Christian Kummerow) organized. IPWG provided formal response to support a detailed articulation of microwave missions with different frequencies in the CGMS baseline and risk assessment. Support material to be used for the formulation of the MW mission details for RA and CGMS Baseline. 7th risk assessment: Addressed with WGII. Recalled in CGMS WGII IS#3 to WGII who will address it at their IS#4 session on 24 Feb 2025. Chair of WGClimate to review. IS#2: Heikki Pohjola contacted WGII and presented the action in WGII intersessional meeting. WGII rapporteur Paolo Ruti (EUMESAT) confirmed that WGII is working on this action. Next WGII intersessional is on 21 Jan 2025. Minutes of WGII IS of 19 Nov 2024: Support to WGIII, the need for articulating MW missions with different frequencies in the CGMS baseline and risk assessment in the future - need for considering the different types of microwave instruments and their applications. Discussion highlighted the need for a more detailed representation of microwave missions in the CGMS baseline and risk assessment, considering different frequencies and their applications. Next steps: Identification of 1-2 people from WGII to support WGIII in the analysis of microwave missions with different frequencies. This team should focus on identifying key frequencies and their applications and propose a method for incorporating this information into the CGMS baseline and risk assessment. Addressed by Heikki/WMO at the WGII intersessional on 19 Nov 2024 WGIII IS#1: Heikki/WMO to draft an input for sending to WGII leading entity. | 2026 3-5 Feb: 8th risk assessment (Q1/2026) | ONGOING
WGIII for WGII/GHG TT | 7.1 | WGIII/52.04 | WGIII for WGII: GHG TT to review representation of SWIR missions for CH4, and CO2 in the CGMS baseline and the risk assessment | 8RAWS: Progress expected for the next WGIII IS on 11 March. , Needs more preparatory work with GHG TT Chair and WMO. GHG satellite mission portal: ceos.org/ghg Work ongoing to have a follow up meeting with Wenying Su WGII nominated Wenying Su (WGClimate) as a focal point for their support. 7th risk assessment: Addressed with WGII. (Action rephrased at the 7th RAWS). Recalled in CGMS WGII IS#3 to WGII who will address it at their IS#4 session on 24 Feb 2025. simon.elliot@eumetsat.int IS#2: feedback from GHG TT still pending Heikki/WMO contacted GHG TT focal point (Simon Elliott) to communicate request to GHG TT. WGIII IS#1: Heikki/WMO to draft an input for sending to the GHG TT and SWCG leading entities. | 2026 3-5 Feb: 8th risk assessment (Q1/2026) | ONGOING
CMA | 3.2 | WGIII/53.01 | CMA to present in CGMS-54 WGIII meeting RO impact studies of commercial RO data assimilated in their NWP model | 8RAWS: CMA confirmed. WGIII IS#2 expected to be available for CGMS-54 WG meetings in April 2026 | CGMS-54 | ONGOING
CGMS members | 4 | WGIII/53.02 | CGMS members to review focus areas of the CGMS position paper on WIGOS Vision 2050 update | 8RAWS: Sharing of latest version. To be presented to WGIII for recommendation to plenary. CGMSSEC to circulate the statement to members and to ISWGs leads WGIII IS#2 CGMSSEC will iterate the statement before end of 2025 The CGMS Secretariat is preparing the draft of the CGMS input to the WIGOS Vision 2040 update to be circulated to members for review. It will then be provided to the WMO WIGOS Vision update workshop late September. | End 2025 | ONGOING
(Sep 2025)
()
CMA | 7 | WGIII/53.03 | CMA to present Best practices for regional EW4ALL for the benefit of the local government in CGMS-54 WGIV meeting. | Action closed in the framework of WGIII, transferred to the WGIV LOA. | CGMS-54 | CLOSED (action transferred to WGIV LOA)
WGIII | WGIII IS | - | Review and update of CGMS best practices on relationship with the private sector on commercial data purchases | WMO will contact Daniel Kull (Director of the Development Partnerships Office (DPO)), to participate in the workshop for the private sector engagement updates agenda item. He will work as a DPO focal point between WGIII and WMO. WGIII IS#2 Decision to made on the occasion of the 8th RAWS whether to update the BP by CGMS-54 or CGMS-55. To be added as a "standing" CGMS WGIII action (to the ordinary action list) | CGMS-55 (2027) or later as needed | OPEN
|  |  | 7th risk assessment WS actions | -2025
WMO | 4 | 7RAWS-1 | WMO to provide a summary of the most critical gaps in WIGOS based on WMO Gap Analysis | Provided by WMO in CGMS-53-WMO-WP-07, ppt | CGMS-53 WGIII | CLOSED
SWCG | 4 | 7RAWS-2 | The SWCG to review WMO space weather gap analysis and inform WMO on missing or incorrect (NRT) data availability indicated in the WMO Gap Analysis document. | 8RAWS: Discussed and finalisation expected at SWCG session in April. WGIII IS#2 CGMSSEC to send all relevant risk assessment actions to the SWCG | CGMS-53 SWCG | ONGOING
EUM | 5 | 7RAWS-3 | EUMETSAT to provide updated graphics of the RO profiles available per satellite mission vs time. | Provided to the risk assessment book captain (NOAA/Melissa Johnson) | CGMS-53 WGIII | CLOSED
NASA, JAXA | 5 | 7RAWS-4 | NASA and JAXA to provide a coordinated additional information on possible GPM continuation mission. | 8RAWS: Presentation by NASA, GPM to continue to early 2030s. JAXA will present to WG session in April their PPM mission. NASA provided updates: GPM performed two orbit boost manoeuvres in November 2023 to raise its altitude and restore its lifespan closer to the original estimates of ending in the early 2030s. NASA is working with JAXA to maintain continuity of this important precipitation measurement. Postponed to CGMS-54 | CGMS-54 | CLOSED?
NASA | 5 | 7RAWS-5 | NASA on IMAP mission and if its data is compliant with CGMS Baseline criteria. | The latency requirement is <5 minutes for data that is received on the ground and then processed and delivered to the space weather community. The space weather data set only includes the data from the five space weather relevant instruments and the necessary spacecraft ancillary data to make it useful. Those instruments include CoDICE (Compact Dual Ion Composition Experiment), HIT (High-energy Ion Telescope), SWAPI (Solar Wind and Pickup Ion), SWE (Solar Wind Electron), and MAG (Magnetometer). I-ALiRT is dependent on the establishment of a global ground station network. NASA currently has agreements with South Korea and Germany and continue to work on agreements with partners in the southern hemisphere and South America; however, having global coverage at launch in September is not anticipated. Expected to be addressed in the course of and up to CGMS-54 | 2026 3-5 Feb: 8th risk assessment | CLOSED
(CGMS-54 WGIII)
CGMSSEC | 7th risk assessment WS | 7RAWS-6 | CGMSSEC to contact ESA to clarify EarthCare instruments and to which observations it should be included in the risk assessment | EarthCARE has been removed from the risk assessment for Sub-Millimeter Ice Cloud Imager and Precipitation Radar, and has been added to the flyout for LEO Imagers | CGMS-53 WGIII | CLOSED
Action on CMA | 7th risk assessment WS | 7RAWS-7 | CMA to confirm if current GEO slots in the Baseline document are compliant with the locations of CMA satellites. | CMA confirmed the baseline document is currently compliant. | CGMS-53 WGIII | CLOSED
Action on SWCG | 7th risk assessment WS | 7RAWS-8 | The SWCG to make a recommendation to WGIII how to separate RO and Ionospheric Electron Density profiles in the CGMS Baseline and the risk assessment documents. | 8RAWS: Preliminary input shared by SWCG and added to the master file - further finalisation by SWCG in April WG session for confirmation. WGIII IS#2 CGMSSEC to send all relevant risk assessment actions to the SWCG Expected to be addressed in the course of and up to CGMS-54 | 2026 3-5 Feb: 8th risk assessment (Q1/2026) | ONGOING
(CGMS-54)
Action on SWCG | 7th risk assessment WS | 7RAWS-9 | The SWCG to define how to add each satellite position in the attributes of the in-situ measurements of CGMS Baseline. | SWCG complemented the baseline document as necessary at this stage. | CGMS-53 SWCG | CLOSED
Action on NASA/ESA | 7th risk assessment WS | 7RAWS-10 | NASA and ESA to confirm if the L5 JEDI mission and its data is compliant with CGMS Baseline criteria. | 8RAWS: ESA has confirmed. NASA’s final confirmation pending. NASA is contributing the JEDI instrument to ESA’s Vigil mission, which will produce data for both a low latency operational channel and the higher latency science data channel. For Vigil operational data, ESA have a <5min latency 24/7 requirement for the operational data that will go through ground stations to the forecasting offices. NOAA will be responsible for the official processing of CCOR-3 data and for distributing to their partners and customers. If ESA has clarifying information about Vigil – as the mission lead – NASA would defer to that. Expected to be addressed in the course of and up to CGMS-54 | 2026 3-5 Feb: 8th risk assessment | ONGOING
(CGMS-54 WGIII)
Action on ESA | 7th risk assessment WS | 7RAWS-11 | ESA to (re)confirm if Vigil data is compliant with CGMS Baseline criteria, and if its instruments could be added to the plasma analyser and interplanetary magnetometer measurement of the CGMS Baseline | E-mail from J-P Luntamaa/ESA: He confirms that ESA Vigil mission data from the baseline instruments is compliant with the CGMS Baseline principles. This compliancy applies to the following Vigil instruments: Coronagraph (CCOR) Heliospheric Imager (HI) Magnetograph (PMI) Solar wind Plasma Analyser (PLA) Magnetometer (MAG) Data from CCOR will remain owned by NOAA and they will also handle the data dissemination to the users. NOAA has confirmed that all NOAA data will be compliant with CGMS Baseline. | CGMS-53 WGIII/plenary | CLOSED
Action on WGII | 7th risk assessment WS | 7RAWS-12 | WGII to investigate other capabilities for UV limb sounding to complement JPSS | 8RAWS: Status shared. WGIII IS#2 CGMSSEC to send all relevant risk assessment actions to the WGII Action transferred to WGII for review up to CGMS-54 (but remains monitored by WGIII) | 2026 3-5 Feb: 8th risk assessment | ONGOING
(CGMS-54)
Action on WGII | 7th risk assessment WS | 7RAWS-13 | WGII to study and report back to WGIII the need of top of the atmosphere spectral solar irradiance capabilities to be recorded in CGMS Risk Assessment and Baseline. (Link to HLPP 1.2.1 being addressed by WGII) | 8RAWS: Status shared. WGIII IS#2 CGMSSEC to send all relevant risk assessment actions to the WGII Expected to be addressed in the course of and up to CGMS-54 | CGMS-54 WGII | ONGOING
Action on WGII | 7th risk assessment WS |  | WGII to consider whether observations from geostationary orbit should be added to the CGMS baseline requirements for the broadband short/long wave radiometer (https://cgms-info.org/wp-content/uploads/2021/06/CGMS-Baseline-Sustained-contributions-to-the-observing-of-the-Earth-system-space-environment-and-Sun-v6-1.pdf) | 8RAWS: Discussion will take place in the next WGII IS, report expected in April WG session. | CGMS-54 WGII | ONGOING